## ProForma Instructions
A. | The purchase price is inserted in cell A1. This can be the offered sales price, a negotiated amount, or it may be based on an appraisal. It is also possible that the underlying land title will not change, thus there may be no purchase price and this cell will be zero. In addition, liens or defaults may exist which need to be remedied.
B. | Environmental cleanup action costs are input into cells B1 through B3. These costs may be defined already as part of the cleanup plan or they may need to be estimated. Cell B4 will add these three lines together. Cell B4 sums the remedial action costs.
C. | If new construction is involved in the project, complete lines C1 through C5. Estimate the square feet to be constructed and the cost per square foot by building type. Leave unused building categories blank or delete those lines. Worksheets detailing costs will likely be needed to identify and support the various cost elements in the pro forma. Costs can include site clearing and preparation, foundation work, structural and exterior work, mechanicals, and interior finishing. Ongoing maintenance costs and upfront infrastructure costs may require funding prior to construction or during the development phase before there are revenues to cover them. Two such examples are fencing and mowing. Cell C6 sums the hard costs for new construction.
D. | Existing buildings are more complicated. Asbestos removal and other preparation may be required. Costs can include demolition or partial demolition with renovations. These projects generally have more unknown or hidden costs and are therefore riskier. Estimated demolition costs are input in cells D1 and D2. Insert renovation costs per square foot by building type into lines D3 through D6. Cell D7 sums the hard costs for existing construction.
E. | This particular pro forma shows two separate development areas. The project may have one or several distinct areas requiring data. Thus, development areas can be added or subtracted. Cell E1 totals the hard costs for all building types.
F. | Soft costs are calculated as a percentage of hard costs. These are shown in line F1. Additional due diligence is required on these types of projects, thus there may be more investigative costs. These can include: reuse analysis, negotiating access rights and project visioning. By this point in the overall evaluation process, some of these soft costs and cleanup action costs have been incurred, thus estimating 20% for soft costs overall for the developer is not an unreasonable estimate. Soft costs for all standard development projects include site plans, engineering, legal, soil testing, architectural plans and marketing plans. A detailed breakdown between disciplines is not needed at this point.
G. | Carry costs represent interest calculated on cash invested or borrowed for development of the property. Interest on the initial purchase will be calculated from the date of transfer, whereas interest on development is calculated based on an average over time. The interest rate should reflect current rates with some adjustment based on the overall risk of the project.
H. | What are the sources of financing? Who is going to cover the costs, especially the earlier costs? How much cash will be needed to promote redevelopment and who will bear the burden of this cost? There may be different levels of financing in different phases. Ensure that these questions are considered.
I. | The purchase price, cleanup action, hard and soft construction costs and carrying costs are totaled at H1. This cell should represent the total anticipated cost of development.
J. | The other half of analyzing the financial viability of a project involves determining its end value. One approach to this is to use the property’s appraised value; this can be based on market comparisons or the property’s potential reuse. Note that this type of valuation can be impacted by environmental conditions, decreasing accuracy or making it altogether impossible to compare to other properties. The second approach is to determine the property’s anticipated revenue stream. Rents, for example, can be estimated per square foot and projected with escalations over time by type of building. This information is gathered and input in lines J1 through J4. Cell J5 provides the total net operating income.
K. | Net operating income can be derived by subtracting operating expenses from rental rates. Obtain operating expenses and management fees on a per square foot basis using industry standards by building type. Vacancy rates are figured by building type and local market conditions as well as type of tenants anticipated. In some cases, it may be necessary to include amounts for longer term cleanup action expenses, ongoing special cleanup action and maintenance costs, reserves and/or environmental insurance. If these are necessary, cell J8 will calculate an adjusted net operating income. Otherwise, cell J5 will serve this function.
L. | The capitalization rate is used to calculate a rough project valuation. The rate used is based on the market and risk involved. Consult with industry professionals.
M. | Cell K1 calculates the project’s estimated completed value less development costs. A cash return on investment is also calculated in cell L1.

## ProForma Assumptions
Assumptions
Enter information in cells outlined in red, as appropriate
Total Land Area
Existing Building size |  | 0
Purchase Price |  | 0
Cost of remediation
Phase I |  | 0 |  | 0
PhaseII |  | 0
Remediation |  | 0
Construction Costs
Re-Use/cost per sf
Demolition | psf | 25
Retail | psf | 50
Office | psf | 80
Industrial | psf | 30
Residential | psf | 50
New Construction/cost per sf
Retail | psf | 60
Office | psf | 100
Industrial | psf | 50
Residential | psf | 60
Parking | spot | 1200
Soft Costs | 20% | of Hard Costs
Carrying Costs
Period | 24 | months
Rate | 8.5%
Income
Retail | psf | 18
Office | psf | 18
Industrial | psf | 5.5
Residential - rent | per unit | 1800 | assume 2,000 sf per unit including common areas
Vacancy Rate | 5%
Capitalization Rate | 8%

## ProForma
Real Estate Pro Forma for Redevelopment Project
Directions: | Enter information in cells outlined in red, as appropriate
PROJECT COSTS | [6 empty] | Cell
Purchase Price | [5 empty] | 0 | A1 | Acquisition Price, may be based on appraised value minus remediation
Remedial Action Costs For Project |  |  | Remedial Action (Area 1) |  |  | 0 | B1 | Cost of implementing remedial action (e.g., soil or water cleanup)
|  |  | Remedial Action (Area 2) |  |  | 0 | B2 | Cost of implementing remedial action (e.g., soil or water cleanup)
|  |  | Total for Remedial Action |  |  | 0 | B3 | Total Remedial Action Cost
Hard Costs
Development Segment 1
New Construction
Retail | Square feet | 0 | Cost/sf | 60 | 0 |  | C1 | Construction cost per sf for retail
Industrial | Square feet | 0 | Cost/sf | 50 | 0 |  | C2 | Construction cost per sf for industrial
Office | Square feet | 0 | Cost/sf | 100 | 0 |  | C3 | Construction cost per sf for office
Residential | Square feet | 0 | Cost/sf | 60 | 0 |  | C4 | Construction cost per sf for residential
Parking | Parking Spots | 0 | Cost/unit | 1200 | 0 |  | C5 | Construction cost for parking per space
| Total Hard Costs (Development Segment 1) |  |  |  |  | 0 | C6 | Total Construction Cost Area 1
Development Segment 2
Existing Building
Asbestos Removal | abatement of materials in building - lump sum |  |  | 0 | 0 |  | D1 | Lump sum cost of asbestos removal
Demolition | Square feet | 0 | Cost/sf | 25 | 0 |  | D2 | Demolition cost per sf
Renovation Costs
Retail | Square feet | 0 | Cost/sf | 50 | 0 |  | D3 | Renovation cost per sf of retail
Industrial | Square feet | 0 | Cost/sf | 30 | 0 |  | D4 | Renovation cost per sf of industrial
Office | Square feet | 0 | Cost/sf | 80 | 0 |  | D5 | Renovation cost per sf of office
Residential | Square feet | 0 | Cost/sf | 50 | 0 |  | D6 | Renovation cost per sf of residential
| Total Hard Costs (Development Segment 2) |  |  |  |  | 0 | D7 | Total Rehab and Construction Cost Area 2
| Total residential units @ |  | 2000 | sf |  | 0 | D8
Total Hard Costs for Development Segments 1 and 2 | [5 empty] | 0 | D9 | Total Construction Costs Areas 1 + 2
Total Hard Costs for Development Segments 1 and 2 + Remedial Action Costs | [5 empty] | 0 | E1 | Total Construction Costs Areas 1 + 2 plus remedial action costs
Soft Costs | % of hard costs and remediation costs |  |  | 20% |  | 0 | F1 | Softs costs +/- 20% of construction costs
CARRY COSTS
[5 empty] | Carrying cost |  |  | Interest costs on land acquisition for two years
| Purchase Price |  | 0 |  | 0
| Months |  | 24
| Rate |  | 8.5%
| Soft + Hard Costs + Remediation |  | 0 |  | 0 |  |  | Interest Costs on construction, rehab and remediation
| Months |  | 24 |  |  |  |  | (B4+E1+F1 X % per month X # of months
| Rate |  | 8.5%
|  |  |  | Total | 0
TOTAL DEVELOPMENT COSTS | [5 empty] | 0 | H1 | Total of all development costs
PROJECT VALUE
Net Operating Income
|  |  |  | Rent/sf | Total Income
| Industrial Sq.Feet | 0 |  | 5.5 | 0 |  | J1 | Total industrial sf X estimated net lease rate per year
| Office Sq Feet | 0 |  | 18 | 0 |  | J2 | Total office sf X estimated net lease rate per year
| Retail Use Sq Feet | 0 |  | 18 | 0 |  | J3 | Total retail sf X estimated net lease rate per year
| Total units | 0 |  |  | 0 |  | J4 | Total residential units X estimated annual rent
| Net Operating Income |  |  |  | 0 |  | J5 | Total of annual net rental income
| Less Vacancy | 5% |  |  | 0
| Less Long Term Remediation Operating Expenses |  |  |  | 0 |  | J6 | Post remedial action operation, monitoring, and maintenance
| Less Environmental Insurance |  |  |  | 0 |  | J7 | Environmental insurance premium
| Adjusted Net Operating Income |  |  |  | 0 |  | J8 | Net Operating cincome minus vacancy %,
minus cost of ongoing remdiation, minus cost of environmental insurance
Capitalization Rate |  |  |  |  | 8%
PROJECT VALUE COMPLETED AND OCCUPIED
[6 empty] | 0 | K1 | Adjusted NOI divided be capitalization rate reflecting yield and risk
PROFIT | [5 empty] | 0 | L1 | Project completed value minus total of all development costs
Cash on Cash Return
[6 empty] | 0% |  | Profit as % of Total Development Cost

## Sources and Uses
SAMPLE
SOURCES AND USES OF FUNDS
USES OF FUNDS |  |  | SOURCES OF FUNDS
Acquisition |  | 0 | Construction Sources of Funds
Transaction Costs |  | 0
Total Acquisition Costs |  | 0 | 1st Construction Loan | 0
|  |  | 2nd Construction Loan | 0
Hard Costs |  |  | Developer Equity | 0
Construction |  | 0 | Equity from Federal Tax Credits | 0
General Conditions |  | 0 | Equity from State Tax Credits | 0
Developer fee |  | 0 | Grant Source #1 | 0
Demolition/Property Improvement |  | 0 | Grant Source #2 | 0
Remediation |  | 0 | Other | 0
Hard Cost Contingency | 10% | 0 | Deferred Developer Fee | 0
Total Building Loan Hard Cost |  | 0 | TOTAL CONSTRUCTION SOURCES | 0
Project's Soft Costs |  |  | Permanent Sources of Funds
Borrower's A/E Fee |  | 0
Bank Engineer |  | 0 | Ist Permanent Mortgage | 0
Developer Owner's Representative |  | 0 | 2nd Permanent Mortgage | 0
Bank Legal |  | 0 | Developer Equity | 0
Developer Legal |  | 0 | Equity from Federal Tax Credits | 0
Accounting |  | 0 | Equity from State Tax Credits | 0
Environmental Phase I |  | 0 | Grant Source #1 | 0
Environmental Phase II and III |  | 0 | Grant Source #2 | 0
Other Environmental Professional Fees |  | 0 | Other | 0
Survey |  | 0 | Deferred Developer Fee | 0
Title Insurance |  | 0 | TOTAL PERMANENT SOURCES | 0
Appraisal |  | 0
Bank Commitment Fee |  | 0
Construction Interest |  | 0
Insurance |  | 0
Real Estate Taxes |  | 0
Building Permits |  | 0
Other |  | 0
Letter of Credit/Bond Fee |  | 0
Soft Cost Contingency | 10% | 0
Other |  | 0
Total Building Loan Soft Costs |  | 0
Operating and Lease-up Reserve |  | 0
TOTAL USES OF FUNDS |  | 0