## State or MSA
Sample State or MSA Climate Planning Timeline and Milestones
| ACTIVITY | Months
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Ongoing Processes and Meetings
Develop Quality Assurance Plan | bar: Months 1 to Months 2
Interagency Meetings | bar: Months 1; Months 3; Months 5; Months 7; Months 10; Months 13; Months 16; Months 19; Months 22; Months 28; Months 34; Months 40; Months 46
Stakeholder Meetings | bar: Months 2; Months 4; Months 6; Months 10; Months 13; Months 16; Months 19; Months 30; Months 42
Meetings with Municipal Partners | bar: Months 2; Months 4; Months 6; Months 11; Months 14; Months 20; Months 26; Months 38; Months 46
Quarterly Reports | bar: Months 4; Months 7; Months 10; Months 13; Months 16; Months 19; Months 22; Months 25; Months 28; Months 31; Months 34; Months 37; Months 40; Months 43; Months 46
Priority Climate Action Plan | bar: Months 1 to Months 8
GHG Inventory/Analysis | bar: Months 1 to Months 2
GHG Measure Selection | bar: Months 2 to Months 7
Quantification of GHG and LI-DC Benefits | bar: Months 4 to Months 8
Review of Authority | bar: Months 3 to Months 5
Leveraging Funding Opportunities and Workforce Analysis | bar: Months 6 to Months 7
Publish PCAP | bar: Months 8
Comprehensive Climate Action Plan | bar: Months 9 to Months 24
GHG Inventory and Projections | bar: Months 9 to Months 11
GHG Target Setting | bar: Months 11 to Months 13
GHG Measure Selection and Quantification | bar: Months 13 to Months 22
Benefits and LI-DC Benefits Analyses | bar: Months 16 to Months 22
Review of Authority and Funding Opportunities | bar: Months 17 to Months 20
Workforce Analysis and Strategy | bar: Months 21 to Months 23
Publish CCAP | bar: Months 24
Status Report and Ongoing Activities | bar: Months 25 to Months 48
Update Emissions Analyses | bar: Months 33 to Months 36; Months 40 to Months 45
Update Workforce Analysis | bar: Months 35 to Months 36; Months 42 to Months 46
Assess Implementation Status | bar: Months 35 to Months 36; Months 43 to Months 46
Develop Next Steps and Status Report | bar: Months 44 to Months 47
Publish Status Report | bar: Months 48