## Overview
Legend
Activity performed in month
Text | Example input: note - these are example inputs and are not meant to be included in implementation workplans nor exauhstive of steps applicants must take
Introduction:
This Excel Workbook is an optional template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative. Please see details in Section IV and V of the Notice of Funding Opportunity for additional information about the application components and evaluation criteria.
There are 5 tabs in this template - one tab for each plan and strategy in the Program Strategy Narrative. Within each tab, there are optional sections that correspond to each of the themes of the criteria points in the Evaluative Criteria of the Notice of Funding Opportunity. EPA has drafted example activities and timelines to illustrate how to use the template.
To help demonstrate to EPA how applicants plan on engaging with relevant stakeholders during the program planning stage and which program planning services applicants anticipate using, this template includes space for applicants to explain for each activity relevant stakeholders which will be engaged during the activity and relevant program planning services.
Please refer back to the Notice of Funding Opportunity for additional guidance on how the worksheet can help complete the Program Narrative.
Instructions:
For each tab, below is a description of the steps an applicant should complete to finish the template. Applicants should add and subtract rows as needed.
- In column B, consider grouping activities described in column C (explained below) according to the
- In column C, fill in activities the program will complete in the first year of the program; add a row for each activity; an activity could be a discrete piece of analysis needed to refine plans/strategies detailed in the Program Narrative; a specific engagement with an important stakeholder; a process like a Request for Proposals or hiring a program manager; and any other type of activity which would be helpful to complete before launching the program.
- In column D, describe the type of tools and program planning services the program will use to complete the activity (if applicable)
- In column E, write or describe the stakeholders that will be engaged to complete the activity (if applicable)
- In columns F through Q, indicate with a colored cell when the activity will occur; consider whether the activity is repeated on some frequency (e.g., a quarterly briefing); consider indicated clearly in the Financial Assistance Strategy workplan when the program will begin offering financial assistance to customers

## Program Planning Workplan-->
Page intentionally left blank

## 1.2 Meaningful Benefits
Program Planning Timeline and Workplan - Section 1.2 Meaningful Benefits Plan
An OPTIONAL template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative
Year 1 (program planning)
Program Strategy Narrative section | Activities to complete program planning | Anticipated services and tools that support program design | Stakeholders to be engaged during planning phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Household savings (10 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 6
| Activity 2 |  | Hold monthly briefing meetings with stakeholder-A to solicit input on program design | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 7
Equitable access to solar (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 2
Activity 2 | bar: Year 1 (program planning) Month 3 to Year 1 (program planning) Month 8
Resilience benefits (5 points) | Activity 1 | Contract with National Labs to perform analysis to inform program design | bar: Year 1 (program planning) Month 1; Year 1 (program planning) Month 3; Year 1 (program planning) Month 5; Year 1 (program planning) Month 7; Year 1 (program planning) Month 9; Year 1 (program planning) Month 11
Activity 2 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 4
Community ownership (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 3
Activity 2 | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 6
Workforce development and entrepreneurship (5 points) | Activity 1
Activity 2 | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 6

## 1.3 DG Market Strategy
Program Planning Timeline and Workplan - Section 1.3 Distributed Solar Market Strategy
An OPTIONAL template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative
Year 1 (program planning)
Program Strategy Narrative section | Activities to complete program planning | Anticipated services and tools that support program design | Stakeholders to be engaged during planning phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Net metering (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 6
| Activity 2 |  | Hold monthly briefing meetings with stakeholder-A to solicit input on program design | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 7
Third-party ownership (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 2
Activity 2 | bar: Year 1 (program planning) Month 3 to Year 1 (program planning) Month 8
Interconnection processes (5 points) | Activity 1 | Contract with National Labs to perform analysis to inform program design | bar: Year 1 (program planning) Month 1; Year 1 (program planning) Month 3; Year 1 (program planning) Month 5; Year 1 (program planning) Month 7; Year 1 (program planning) Month 9; Year 1 (program planning) Month 11
Activity 2 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 4
Renewable portfolio standard (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 9
Activity 2 | bar: Year 1 (program planning) Month 8 to Year 1 (program planning) Month 12
Enabling regulatory frameworks for community solar (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 3
Activity 2 | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 6
Understanding of jurisdictional nuances (5 points) | Activity 1
Activity 2 | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 6

## 1.4 Financial Assistance Strat
Program Planning Timeline and Workplan - Section 1.4 Financial Assistance Strategy
An OPTIONAL template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative
Year 1 (program planning)
Program Strategy Narrative section | Activities to complete program planning | Anticipated services and tools that support program design | Stakeholders to be engaged during planning phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Financial assistance model (10 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 6
| Activity 2 |  | Hold monthly briefing meetings with stakeholder-A to solicit input on program design | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 7
Financial assistance leveraging strategy (10 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 2
Activity 2 | bar: Year 1 (program planning) Month 3 to Year 1 (program planning) Month 8
Associated storage and enabling upgrades financial assistance strategy (5 points) | Activity 1 | Contract with National Labs to perform analysis to inform program design | bar: Year 1 (program planning) Month 1; Year 1 (program planning) Month 3; Year 1 (program planning) Month 5; Year 1 (program planning) Month 7; Year 1 (program planning) Month 9; Year 1 (program planning) Month 11
Activity 2 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 4
Long-term impacts of projects supported by financial assistance strategy (i.e., O&M strategy and affordability strategy) (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 3
Activity 2 | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 6

## 1.5 Project-Deployment TA
Program Planning Timeline and Workplan - Section 1.5 Project-Deployment Technical Assistance Strategy
An OPTIONAL template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative
Year 1 (program planning)
Program Strategy Narrative section | Activities to complete program planning | Anticipated services and tools that support program design | Stakeholders to be engaged during planning phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Workforce development (10 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 6
| Activity 2 |  | Hold monthly briefing meetings with stakeholder-A to solicit input on program design | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 7
Interconnection technical assistance (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 2
Activity 2 | bar: Year 1 (program planning) Month 3 to Year 1 (program planning) Month 8
Resilient project siting, land-use, permitting, building codes, inspection, and quality control technical assistance (5 points) | Activity 1 | Contract with National Labs to perform analysis to inform program design | bar: Year 1 (program planning) Month 1; Year 1 (program planning) Month 3; Year 1 (program planning) Month 5; Year 1 (program planning) Month 7; Year 1 (program planning) Month 9; Year 1 (program planning) Month 11
Activity 2 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 4

## 1.6 Equitable Access
Program Planning Timeline and Workplan - Section 1.6 Equitable Access and Meaningful Involvement Plan
An OPTIONAL template for applicants to fill in and submit in the Application Materials, Attachment D: Program Planning Timeline and Workplan described in Section 1.7 of the Program Narrative
Year 1 (program planning)
Program Strategy Narrative section | Activities to complete program planning | Anticipated services and tools that support program design | Stakeholders to be engaged during planning phase | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Strategy to maximize equitable program reach (10 points) | Activity 1 | Contract with National Labs to perform analysis to inform program design | bar: Year 1 (program planning) Month 1; Year 1 (program planning) Month 3; Year 1 (program planning) Month 5; Year 1 (program planning) Month 7; Year 1 (program planning) Month 9; Year 1 (program planning) Month 11
Activity 2 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 4
Participatory governance strategy (10 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 6
| Activity 2 |  | Hold monthly briefing meetings with stakeholder-A to solicit input on program design | bar: Year 1 (program planning) Month 4 to Year 1 (program planning) Month 7
Education, outreach, and community involvement strategy (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 2
Activity 2 | bar: Year 1 (program planning) Month 3 to Year 1 (program planning) Month 8
Customer acquisition and management strategy (5 points) | Activity 1 | bar: Year 1 (program planning) Month 1 to Year 1 (program planning) Month 9
Activity 2 | bar: Year 1 (program planning) Month 8 to Year 1 (program planning) Month 12

## Incomplete - Comment Log table (hidden)
Media: | NPM: | Regional Division: | EPA Goal: | EPA Objective: | Workplan Component | Commitment FY | Workplan Commitment | Commitment Comment | Outcome | Status | Status Comment | EPA Comment | State Comment | Comment Date | Target Completion
Air & Radiation | OAR | ARD | Goal 1 - Core Mission | Objective 1.1 – Improve Air Quality | Ozone, PM2.5, PM10, and CO | FY18 | Continue participation in EPA's AIRNOW program. Submit real-time pollutant data and provide forecasts and alerts. By March 1, 2018, work with EPA to enable Twitter and real-time notification features of EnviroFlash. Attend R1 air quality outreach and forecasting workshop, if held, either in person or remotely. Attend EPA's National Air Quality Conference. (FY'18-19 DRAFT OAR NPM Guidance: NAAQS, 2.1.1.3 Other, #1; and Ambient Air Monitoring for Criteria Pollutants, 2.4.1, #8)
Air & Radiation | OAR | ARD | Goal 1 - Core Mission | Objective 1.1 – Improve Air Quality | Ozone, PM2.5, PM10, and CO | FY19
Air & Radiation | OAR | ARD | Goal 1 - Core Mission | Objective 1.1 – Improve Air Quality | Ozone, PM2.5, PM10, and CO | FY19 | For all future revisions to the SIP, work to implement the recommendations in the final Standard Operating Procedures document developed by EPA Region 1 and the New England states. |  |  | Complete |  |  | NH will implement these recommendations

## Standardized Terms (hidden)
Standardized Term | Definition | Also Known As
Workplan Component | A negotiated set or group of work plan commitments established in the grant agreement. A work plan may have one or more work plan components | Program Area
Workplan Commitment | The outputs and outcomes associated with each work plan component, as established in the grant agreement | Activity | Planned Accomplishments/Requirements | Output
Status | Short defined list of status options. Detailed status information can be captured in the comment field
Comment
Subcomponent | a subgrouping of commitments under a larger workplan component | Related Measure