| Indian Environmental General Assistance Program SAMPLE FY27/FY28 Work Plan Tribe: Region: Region 10 Work Plan Period Begin: 10/1/2026 Period End: 9/30/2028 |  |  |  |
| --- | --- | --- | --- |
| Work Plan Component Number: 1 Work Plan Component Title: Management of Environmental Office Personnel: Environmental Coordinator, Assistant, Bookkeeper ETEP Priority Supported: All Priorities |  |  |  |
| Long-Term Outcome(s): - Improved environmental program Intermediate Outcome(s): - Increased capacity through training - Improved understanding of community concerns - Excellent grant management |  |  |  |
| Estimated Component Cost: |  | Estimated Work Years: |  |
| COMMITMENTS |  | END DATE | OUTPUTS AND DELIVERABLES |
| 1.1 | Environmental Assistant will conduct an annual community assessment to help inform ETEP priorities, work plans, and grant funding requests. | 12/30/2026 12/30/2027 | Share results in quarterly newsletter and progress report. |
| 1.2 | Environmental Coordinator will attend a grant-writing seminar and submit applications for two new environmental grants. | 3/30/2027 | Submit training certificate to EPA Project Officer. |
| 1.3 | Environmental Coordinator & Assistant will attend the Alaska Tribal Conference on Environmental Management in Anchorage March 2027 and March 2028. | 3/30/2027 3/30/2028 | Submit Trip Reports to the EPA Project Officer and the Tribal Council |
| 1.4 | Environmental Coordinator will work with the Council and EPA to review/revise EPA-Tribal Environmental Plan (ETEP). | 9/30/2027 9/30/2028 | Submit revised/updated ETEP to the Council and EPA. |
| 1.5 | Environmental Coordinator and Bookkeeper will prepare the annual Federal Financial Report (FFR), SF-425. | 1/30/2027 1/30/2028 | Submit annual FFR to EPA Project Officer and rtpfc-grants@epa.gov. |
| 1.6 | Environmental Coordinator, Assistant, Bookkeeper, Accountant, and/or Tribal Administrator will participate, as appropriate, in EPA Region 10 GAP webinars and teleconferences. Share relevant information with the community through quarterly newsletters, weekly social media, etc. | 9/30/2027 9/30/2028 | Document activities in monthly employee reports to Tribal Council and in quarterly progress reports to EPA. Submit newsletters to Council and EPA Project Officer. |
| 1.7 | Environmental Coordinator will submit quarterly progress reports 1/30, 4/30, 7/30, and 10/30. | 9/30/2027 9/30/2028 | Submit reports to EPA Project Officer and the Tribal Council. |
| 1.8 |  | Environmental Coordinator will begin preparing an application for FY29-FY32 funding. | 9/30/2028 | Discuss drafts with Tribal Council and EPA Project Officer. |