## Overview
Introduction:
This Excel Spreadsheet is provided to aid Climate Pollution Reduction Grant implementation grant applicants in developing the required budget table(s) within the budget narrative. Applicants may submit a budget spreadsheet (no page limit) with their application.
The individual worksheets are formatted for 1 page width of 8.5" x 11" landscape orientation.
Instructions:
The template contains 5 tabs (titled "Measure 1 Budget" through "Measure 5 Budget") where applicants can create budgets for up to 5 discrete GHG measures contained in their application. Applicants should leave excess tabs blank (i.e., if an application is for a single GHG measure, only Tab 1 should contain any numerical entries.) The Consolidated Budget tab will automatically sum budget totals across all GHG measure Tabs. If an application includes more than 5 GHG measures, users may add duplicate tabs, but will need to manually update the formulas contained on the Consolidated Budget tab.
Measure Tab Instructions:
Below is a description of the steps an applicant should complete to finish each measure tab of the template.
- In column C, provide itemized costs descriptions in each cost category. Insert or delete rows as needed.
- In columns D through H, fill in the cost for the line item per year - personnel, fringe benefits, travel, equipment, installation, or labor supplies, contractual costs, and other direct costs (i.e., subawards, participant support costs), and indirect costs for each applicable year. Subtotals will calculate automatically.
- Column J will automatically calculate the total cost for the line item for the entire measure, including subtotals for each budget category - personnel, fringe benefits, travel, equipment, installation, or labor supplies, contractual costs, and other direct costs (i.e., subawards, participant support costs), and indirect costs.
Please check all formulas and calculations before finalizing your budget tables.
Consolidated Budget Instructions:
This table will update automatically based on the budget detail entered in the tabs for measures 1-5. If your application includes more than 5 individual measures, you will need to add additional tabs, update the formulas below, and add additional lines to the "Budget by Project" table to include the additional measures.

## Consolidated Budget
Consolidated Budget Table
This table will update automatically based on the budget detail entered in the tabs for measures 1-5. If your application includes more than 5 individual measures, you will need to add additional tabs, update the formulas below, and add additional lines to the "Budget by Project" table to include the additional measures.
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | TOTAL
Direct Costs | TOTAL PERSONNEL | 30297.918 | 21641.37 | 17313.096 | 12984.822 | 4328.274 | 86565.48
| TOTAL FRINGE BENEFITS | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL TRAVEL | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL SUPPLIES | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL CONTRACTUAL | 607783.1375 | 434130.8125 | 347304.65 | 260478.4875 | 86826.1625 | 1736523.25
| TOTAL OTHER | 68215 | 48725 | 38980 | 29235 | 9745 | 194900
| TOTAL DIRECT | 706296.0555 | 504497.1825 | 403597.746 | 302698.3095 | 100899.4365 | 2017988.73
| TOTAL INDIRECT | 30367.6032 | 21691.1452 | 17352.9161 | 13014.6871 | 4338.229 | 86764.5806
TOTAL FUNDING |  | 736663.6587 | 526188.3277 | 420950.6621 | 315712.9966 | 105237.6655 | 2104753.3106

## Measure 1 Budget
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | TOTAL
Direct Costs | Personnel
| Deputy Director | 16026.29 | 11447.35 | 9157.88 | 6868.41 | 2289.47 | 45789.4
| Senior Project Manager | 4512.186 | 3222.99 | 2578.392 | 1933.794 | 644.598 | 12891.96
| Senior Planner | 2268.322 | 1620.23 | 1296.184 | 972.138 | 324.046 | 6480.92
| Financial Director | 7491.12 | 5350.8 | 4280.64 | 3210.48 | 1070.16 | 21403.2
| TOTAL PERSONNEL | 30297.918 | 21641.37 | 17313.096 | 12984.822 | 4328.274 | 86565.48
Contractual
| Planning Technical Services | 607783.1375 | 434130.8125 | 347304.65 | 260478.4875 | 86826.1625 | 1736523.25
| TOTAL CONTRACTUAL | 607783.1375 | 434130.8125 | 347304.65 | 260478.4875 | 86826.1625 | 1736523.25
Other
| COG Coalition Members | 68215 | 48725 | 38980 | 29235 | 9745 | 194900
| TOTAL OTHER | 68215 | 48725 | 38980 | 29235 | 9745 | 194900
| TOTAL DIRECT | 638081.0555 | 455772.1825 | 364617.746 | 273463.3095 | 91154.4365 | 1823088.73
Indirect Costs | Indirect Costs
| WestCOG NICRA (100.23%) | 30367.6032 | 21691.1452 | 17352.9161 | 13014.6871 | 4338.229 | 86764.5806
| TOTAL INDIRECT | 30367.6032 | 21691.1452 | 17352.9161 | 13014.6871 | 4338.229 | 86764.5806
TOTAL FUNDING |  | 668448.6587 | 477463.3277 | 381970.6621 | 286477.9966 | 95492.6655 | 2104753.3106
| Annual Rates | 0.35 | 0.25 | 0.2 | 0.15 | 0.05 | 1

## Task Hour Calculator
| Tasks | Project Manager | Land Use Specialist | Supporting Planner | Financial Administrator | Planning Technical Services | COG Coalition Members | Total
1 | Consultant Coordination | 420 | 60 | 0 | 0 | 0 | 185 | 665
2 | COG Coordination | 160 | 26 | 26 | 0 | 260 | 308 | 780
3 | Municipal Coordination | 98 | 21 | 98 | 0 | 6000 | 840 | 7057
4 | Working Group Meetings | 15 | 10 | 10 | 0 | 320 | 280 | 635
5 | Climate Friendly Land Use Tool Box | 21 | 14 | 14 | 0 | 550 | 147 | 746
6 | LIDAC Strategy | 95 | 7 | 0 | 0 | 215 | 189 | 506
7 | 1-1 Technical Support Meetings | 0 | 0 | 0 | 0 | 1500 | 0 | 1500
8 | Regulations and Processes Crafting | 0 | 0 | 0 | 0 | 300 | 0 | 300
9 | Financial Coordination | 0 | 0 | 0 | 480 | 60 | 0 | 540
| Total Hours | 809 | 138 | 148 | 420 | 9205 | 1949 | 12669
| Hourly Rates | 56.6 | 93.42 | 43.79 | 50.96 | 188.65 | 100 | NA
| Total Costs | 45789.4 | 12891.96 | 6480.92 | 21403.2 | 1736523.25 | 194900 | 2017988.73
| WestCOG NICRA (100.23%) | 45894.7156 | 12921.6115 | 6495.8261 | 21452.4274 | 0 | 0 | 86764.5806
| Total Cost | 91684.1156 | 25813.5715 | 12976.7461 | 42855.6274 | 1736523.25 | 194900 | 2104753.3106
| Personnel Total | 86565.48
| Contrctual Total | 1931423.25
| Indirect Total | 86764.5806
| Total Measure Cost | 2104753.3106

## Schedule
|  | 2024 |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
|  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Task 1. | Consultant Coordination
Task 2. | COG Coordination
Task 3. | Municipal Coordination
Task 4. | Working Group Meetings | bar: 2025 1; 2025 4; 2025 7; 2025 10; 2026 1
Task 5. | Climate Friendly Land Use Tool Box | bar: 2026 2 to 2026 6
Task 6. | LIDAC Strategy | bar: 2024 12 to 2025 1; 2025 12 to 2026 1; 2026 12 to 2027 1; 2027 12 to 2028 1; 2028 12 to 2029 1
Task 7. | 1-1 Technical Support Meetings | bar: 2026 7 to 2029 9
Task 8. | Regulations and Processes Crafting | bar: 2026 7 to 2029 9
Task 9. | Financial Coordination
Milestone I. Comple Working Groups
Kick Off Meeting
Milestone II. Publish Land Use Toolbox
Milestone III. Local Adoption
RFP Process
Consultant Selection
Convene Project Council
Drafting of Toolbox
Review Toolbox
Working Group Meeting
Working Group Meeting
Working Group Meeting
Prioritization Process Finalized
Techical Assistance Registration
Public Education Meeting
Public Education Meeting
Public Education Meeting

## Performance Measures
Output/Outcome | Performance Measure
Output. Climate Friendly Land Use Toolbox | Quarterly progress reports following the drafting, reviewing, and publishing of the toolbox.
Outcome. Local Adoption of Land Use Regulations and Processes (50) | Regulations and Processes table of adopted regulations and processes, part of a quarterly process. Target is 50 municipalities.
Output. Case Studies Addendum | Count of each write up following a successful local adoption. Target is 50 over five years.
Outcome. GHG Emissions Reductions. (48,173 MTCO2e/year) | Review of annual permit data to update GHG calculations cross referenced with the Regulations and Processes table.

## Formatted Schedule
Implementation Schedule
| 2024 |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027 |  |  |  | 2028 |  |  |  | 2029
| 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 11 | 12 | 1 | 2 | 11 | 12 | 1 | 2 | 8 | 9
Task 1. | [39 empty] | Consultant Coordination
Task 2. | [39 empty] | COG Coordination
Task 3. | [39 empty] | Municipal Coordination
Task 4. | [39 empty] | Working Group Meetings
Task 5. | [39 empty] | Climate Friendly Land Use Tool Box
Task 6. | [39 empty] | LIDAC Strategy
Task 7. | [39 empty] | 1-1 Technical Support Meetings
Task 8. | [39 empty] | Regulations and Processes Crafting
Task 9. | [39 empty] | Financial Coordination
Milestone I. Comple Working Groups
Kick Off Meeting
Milestone II. Publish Land Use Toolbox
Milestone III. Local Adoption
RFP Process
Consultant Selection
Convene Project Council
Drafting of Toolbox
Review Toolbox
Working Group Meeting
Working Group Meeting
Working Group Meeting
Prioritization Process Finalized
Techical Assistance Registration
Public Education Meeting
Public Education Meeting
Public Education Meeting
Convene Project Council

## Descriptive Schedule
Time | Action | Entities
1 week | Convene Project Council | COG Coalition
6 weeks | RFP Process | WestCOG
2 weeks | Consultant Selection | COG Coalition
1 week | Contract Agreements | Consultant, WestCOG
3 weeks | Kick Off Meeting | Consultant, WestCOG, Coalition
1 year | Working Group Meetings | Consultant, WestCOG, Coalition
3 weeks | Toolbox Data Discovery | Consultant, WestCOG, Coalition
4 weeks | Drafting Toolbox | Consultant, WestCOG
2 weeks | Review Toolbox | Coaltion
1 week | Publish Toolbox | Consultant
3 weeks | Technical Assistance Registration | Consultant, WestCOG, Coalition
2 weeks | Prioritization Process | Consultant, WestCOG, Coalition
3 weeks | Public Education Meeting | Consultant, WestCOG, Coalition
3 years | Case Study Addendum | Consultant
3 years | 1-on-1 Technical Assistance | Consultant