## Overview
Introduction:
This Excel Spreadsheet is provided to aid Climate Pollution Reduction Grant implementation grant applicants in developing the required budget table(s) within the budget narrative. Applicants may submit a budget spreadsheet (no page limit) with their application.
The individual worksheets are formatted for 1 page width of 8.5" x 11" landscape orientation.
Instructions:
The template contains 5 tabs (titled "Measure 1 Budget" through "Measure 5 Budget") where applicants can create budgets for up to 5 discrete GHG measures contained in their application. Applicants should leave excess tabs blank (ie, if an application is for a single GHG measure, only Tab 1 should contain any numerical entries.) The Consolidated Budget tab will automatically sum budget totals across all GHG measure Tabs. If an application includes more than 5 GHG measures, users may add duplicate tabs, but will need to manually update the formulas contained on the Consolidated Budget tab.
Measure Tab Instructions:
Below is a description of the steps an applicant should complete to finish each measure tab of the template.
- In column C, provide itemized costs descriptions in each cost category. Insert or delete rows as needed.
- In columns D through H, fill in the cost for the line item per year - personnel, fringe benefits, travel, equipment, installation, or labor supplies, contractual costs, and other direct costs (i.e., subawards, participant support costs), and indirect costs for each applicable year. Subtotals will calculate automatically.
- Column J will automatically calculate the total cost for the line item for the entire measure, including subtotals for each budget category - personnel, fringe benefits, travel, equipment, installation, or labor supplies, contractual costs, and other direct costs (i.e., subawards, participant support costs), and indirect costs.
Please check all formulas and calculations before finalizing your budget tables.
Consolidated Budget Instructions:
This table will update automatically based on the budget detail entered in the tabs for measures 1-5. If your application includes more than 5 individual measures, you will need to add additional tabs, update the formulas below, and add additional lines to the "Budget by Project" table to include the additional measures.

## Consolidated Budget
Consolidated Budget Table
This table will update automatically based on the budget detail entered in the tabs for measures 1-5. If your application includes more than 5 individual measures, you will need to add additional tabs, update the formulas below, and add additional lines to the "Budget by Project" table to include the additional measures.
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | TOTAL
Direct Costs | TOTAL PERSONNEL | 344278.8204 | 603244.7589 | 621342.1016 | 639982.3647 | 659181.8356 | 2868029.8811
| TOTAL FRINGE BENEFITS | 133580.1823 | 234058.9664 | 241080.7354 | 248313.1575 | 255762.5522 | 1112795.5939
| TOTAL TRAVEL | 72214.7 | 74381.141 | 76612.5752 | 78910.9525 | 81278.2811 | 383397.6498
| TOTAL EQUIPMENT | 58680 | 0 | 0 | 0 | 0 | 58680
| TOTAL SUPPLIES | 38624 | 8530 | 10443.24 | 9780.8 | 3151.5488 | 70529.5888
| TOTAL CONTRACTUAL | 396000 | 891000 | 931000 | 877000 | 915000 | 4010000
| TOTAL OTHER | 429711 | 20923379.82 | 21539081.2146 | 22173253.651 | 22826451.2606 | 87891876.9462
| TOTAL DIRECT | 1473088.7027 | 22734594.6863 | 23419559.8669 | 24027240.9257 | 24740825.4783 | 96395309.6598
| TOTAL INDIRECT | 168206.3689 | 294730.9113 | 303572.8386 | 312680.0238 | 322060.4245 | 1401250.5672
TOTAL FUNDING |  | 1641295.0716 | 23029325.5976 | 23723132.7055 | 24339920.9495 | 25062885.9028 | 97796560.227
BUDGET BY PROJECT
Project Number | Project Name | Total Cost | % of Total
1 | Clean Truck Incentives | 44480096.1788 | 45.48%
2 | ECO Schools | 53316464.0482 | 54.52%
Total |  | 97796560.227 | 100%

## Clean Truck Incentives Budget
Detailed Budget Table
Clean Truck Incentives (CTI) Measure
BUDGET BY FEDERAL FISCAL YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 |  | TOTAL
Direct Costs | Personnel
| New: 1 A/O I - Env Science (Program Manager), 1 FTE, with 3% yearly salary increases (6 months' salary year 1 due to time needed to create and hire) | 48796.765 | 100521.3359 | 103536.976 | 106643.0853 | 109842.3778 |  | 469340.5399
| New: 2 Program Coordinator I's, 2 FTE, with 3% salary increases (6 months' salary year 1 due to time needed to create and hire) | 71191.952 | 146655.4211 | 151055.0838 | 155586.7363 | 160254.3384 |  | 684743.5315
| Existing: 1 Gen I - Env Sci (Bureau Chief), 5% FTE with 3% yearly salary increases | 6122.6474 | 6306.3269 | 6495.5167 | 6690.3822 | 6891.0936 |  | 32505.9668
| Existing: 1 Acct & Auditor A, 10% FTE yearly, with 3% yearly salary increases | 6738.5721 | 6940.7293 | 7148.9512 | 7363.4197 | 7584.3223 |  | 35775.9946
| Existing: 2 A/O I -Env Sci (Program Managers), total of 10% FTE year 1 only, with 3% salary increase | 19290.1696 | 0 | 0 | 0 | 0 |  | 19290.1696
| TOTAL PERSONNEL | 152140.1062 | 260423.8132 | 268236.5276 | 276283.6234 | 284572.1321 |  | 1241656.2025
Fringe Benefits
| New: A/O I - Env Science (Program Manager), 1 FTE, with 3% yearly salary increase | 18933.1448 | 39002.2783 | 40172.3467 | 41377.5171 | 42618.8426 |  | 182104.1295
| New: 2 Program Coordinator I's, 2 FTE, with 3% yearly salary increase | 27622.4774 | 56902.3034 | 58609.3725 | 60367.6537 | 62178.6833 |  | 265680.4902
| Existing: 1 Gen I - Env Sci (Bureau Chief), 0.05 FTE with 3% 2024 salary increase | 2375.5872 | 2446.8548 | 2520.2605 | 2595.8683 | 2673.7443 |  | 12612.3151
| Existing: 1 Acct & Auditor A, 0.05 FTE yearly, with 3% yearly salary increase | 2614.566 | 2693.003 | 2773.7931 | 2857.0068 | 2942.7171 |  | 13881.0859
| Existing: 2 A/O I -Env Sci, 0.1 FTE year 1 only, with 3% 2024 salary increase | 7484.5858 | 0 | 0 | 0 | 0 |  | 7484.5858
| TOTAL FRINGE BENEFITS | 59030.3612 | 101044.4395 | 104075.7727 | 107198.0459 | 110413.9873 |  | 481762.6066
| TOTAL PERSONNEL + FRINGE BENEFITS | 211170.4674 | 361468.2527 | 372312.3003 | 383481.6693 | 394986.1194 | 0 | 1723418.809
Travel
Vehicle travel for community meetings, site visits x 3 staff; 12-13 trips each for 18 days per year
| Mileage for in-state travel (37 trips * 400 miles/trip at $0.66/mi) | 9768 | 10061.04 | 10362.8712 | 10673.7573 | 10993.9701 |  | 51859.6386
| Airfare - ($350/roundtrip x 3 people x 1 trip) + ($700/roundtrip x 3 people x 2 trips) | 5250 | 5407.5 | 5569.725 | 5736.8168 | 5908.9213 |  | 27872.963
| Luggage Fees - $25 per flight @ 9 flights/year | 225 | 231.75 | 238.7025 | 245.8636 | 253.2395 |  | 1194.5556
| Hotel - (6 local nights/staff * 3 staff * $157/night) + (8 non-local nights/staff * 3 staff * $250/night) | 8826 | 9090.78 | 9363.5034 | 9644.4085 | 9933.7408 |  | 46858.4327
| Per Diem - [(37 local trips x 1.5 days/trip) + (11 non-local travel days/staff * 3 staff)] * $59/day | 5221.5 | 5378.145 | 5539.4894 | 5705.674 | 5876.8443 |  | 27721.6526
| Taxi - 120 miles/traveler * 3 travelers/trip * 3 trips * $0.66/mile | 712.8 | 734.184 | 756.2095 | 778.8958 | 802.2627 |  | 3784.352
| Parking - ($20 per non-local travel day * 11 non-local travel days/staff * 3 staff) | 660 | 679.8 | 700.194 | 721.1998 | 742.8358 |  | 3504.0296
| TOTAL TRAVEL | 30663.3 | 31583.199 | 32530.695 | 33506.6158 | 34511.8143 |  | 162795.6241
Equipment
| 2023 Ford F-150 Lightning PRO CrewCab 4WD or similar EV, 50% (to be split with ECO Schools measure) | 29340 | 0 | 0 | 0 | 0 |  | 29340
| TOTAL EQUIPMENT | 29340 | 0 | 0 | 0 | 0 |  | 29340
Supplies
| Level 2 Vehicle Charger, including installation, 50% (to be split with ECO Schools measure) | 2450 | 0 | 0 | 0 | 0 |  | 2450
| Laptop computer, docking station x 3; periodic replacement | 6600 | 0 | 2332 | 2398 | 0 |  | 11330
| Computer supplies x 3 (mouse, keyboard, monitor, cables, connectors, webcam, etc.), periodic replacement | 2256 | 0 | 797.12 | 0 | 892.7744 |  | 3945.8944
| iPhone 15 (for quality camera) x 3, 2 replacements | 2490 | 0 | 0 | 1809.4 | 0 |  | 4299.4
| Flipcharts and meeting supplies (tables; banners; educational material) | 1000 | 1000 | 500 | 235 | 235 |  | 2970
| Paper Supplies/outreach material | 930 | 930 | 500 | 250 | 250 |  | 2860
| Communication Supplies (Fax, Mail, Xerox) | 1000 | 2000 | 1000 | 198 | 198 |  | 4396
| TOTAL SUPPLIES | 16726 | 3930 | 5129.12 | 4890.4 | 1575.7744 | 0 | 32251.2944
Contractual
| Consultant: Community, Tribal nations, and stakeholder outreach and engagement with focus on LIDAC | 48000 | 23000 | 18000 | 16000 | 10000 |  | 115000
| Fleet advisor for approximately 80 fleet assessments | 0 | 420000 | 420000 | 420000 | 420000 |  | 1680000
| Technical analysis to support measuring and tracking progress towards achieving established targets, including calculating and reporting reductions in GHG, NOX, SO2, PM2.5, and PM10 based on VMT and emission factors; technical analysis to assess community and workforce benefits | 50000 | 25000 | 50000 | 25000 | 50000 |  | 200000
| TOTAL CONTRACTUAL | 98000 | 468000 | 488000 | 461000 | 480000 |  | 1995000
OTHER
| Participant support costs - Clean Truck Incentives - approximately 750 vouchers for Class 2b-8 zero-emission trucks and approximately 440 vouchers for level 2 and 3 truck chargers | 0 | 9278722 | 9557083.66 | 9843796.1698 | 10139110.0549 |  | 38818711.8847
| Subaward to NM Dept. of Workforce Solutions to support workforce development boards to address job training and readiness | 200000 | 200000 | 200000 | 200000 | 200000 |  | 1000000
| Per FTE costs - payroll & financial software subscription, phone service, IT services including email, PowerPlatform, internet, software; (6 months year 1 due to time needed to create and hire for positions) | 9453 | 19473.18 | 20057.3754 | 20659.0967 | 21278.8696 |  | 90921.5216
| Video meeting capability: 1 conferencing system with 360-degree camera, speakers, mics, 1 projector | 1700 | 0 | 0 | 0 | 0 |  | 1700
| Full video conferencing license - 3 hosts | 360 | 741.6 | 763.848 | 786.7634 | 810.3663 |  | 3462.5778
| Public Survey License, 3 users | 1350 | 2781 | 2864.43 | 2950.3629 | 3038.8738 |  | 12984.6667
| Project management software license, 3 users | 306 | 612 | 630.36 | 649.2708 | 668.7489 |  | 2866.3797
| TOTAL OTHER | 213169 | 9502329.78 | 9781399.6734 | 10068841.6636 | 10364906.9135 |  | 39930647.0305
| TOTAL DIRECT | 599068.7674 | 10367311.2317 | 10679371.7887 | 10951720.3487 | 11275980.6216 |  | 43873452.758
Indirect Costs | Indirect Costs
|  | 74332.0045 | 127236.825 | 131053.9297 | 134985.5476 | 139035.114 |  | 606643.4208
| TOTAL INDIRECT | 74332.0045 | 127236.825 | 131053.9297 | 134985.5476 | 139035.114 |  | 606643.4208
TOTAL FUNDING |  | 673400.7719 | 10494548.0567 | 10810425.7184 | 11086705.8963 | 11415015.7356 |  | 44480096.1788
Y= year
Where appropriate, costs are adjusted for inflation
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current salary midpoint*1.03 estimated raise*0.5 (6 months to create and hire)
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (current 3/2024 salary midpoint*1.03)*1.03 to account for inflation

## ECO Schools Budget
Detailed Budget Table
ECO Schools Measure
BUDGET BY FEDERAL FISCAL YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 |  | TOTAL
Direct Costs | Personnel
| New: 1 A/O I - Env Science (Program Manager), 1 FTE, with 3% yearly salary increases (6 months salary year 1 due to time needed to create and hire) | 48796.765 | 100521.3359 | 103536.976 | 106643.0853 | 109842.3778 |  | 469340.5399
| New: 1 Program Coordinator II, 1 FTE, with 3%yearly salary increases (6 months salary year 1 due to time needed to create and hire) | 39998.608 | 82397.1325 | 84869.0465 | 87415.1178 | 90037.5714 | 450000 | 384717.4762
| New: 2 Program Coordinator I's, 2 FTE, with 3% yearly salary increases (6 months' salary year 1 due to time needed to create and hire) | 71191.952 | 146655.4211 | 151055.0838 | 155586.7363 | 160254.3384 |  | 684743.5315
| Existing: 1 Gen I - Env Sci (Bureau Chief), 5% FTE with 3% yearly salary increases | 6122.6474 | 6306.3269 | 6495.5167 | 6690.3822 | 6891.0936 |  | 32505.9668
| Existing: 1 Acct & Auditor A, 10% FTE yearly, with 3% yearly salary increases | 6738.5721 | 6940.7293 | 7148.9512 | 7363.4197 | 7584.3223 |  | 35775.9946
| Existing: 2 A/O I -Env Sci (Program Managers), total of 10% FTE year 1 only, with 3% salary increase | 19290.1696 | 0 | 0 | 0 | 0 |  | 19290.1696
| TOTAL PERSONNEL | 192138.7142 | 342820.9457 | 353105.574 | 363698.7413 | 374609.7035 | 450000 | 1626373.6786
Fringe Benefits
| New: 1 A/O I - Env Science (Program Manager), 1 FTE, with 3% yearly salary increases (6 months salary year 1 due to time needed to create and hire) | 18933.1448 | 39002.2783 | 40172.3467 | 41377.5171 | 42618.8426 |  | 182104.1295
| New: 1 Program Coordinator II, 1 FTE, with 3%yearly salary increases (6 months salary year 1 due to time needed to create and hire) | 15519.4599 | 31970.0874 | 32929.19 | 33917.0657 | 34934.5777 |  | 149270.3808
| New: 2 Program Coordinator I's, 2 FTE, with 3% yearly salary increases | 27622.4774 | 56902.3034 | 58609.3725 | 60367.6537 | 62178.6833 |  | 265680.4902
| Existing: 1 Gen I - Env Sci (Bureau Chief), 0.05 FTE with 3% yearly salary increase | 2375.5872 | 2446.8548 | 2520.2605 | 2595.8683 | 2673.7443 |  | 12612.3151
| Existing: 1 Acct & Auditor A, 0.05 FTE yearly, with 3% yearly salary increase | 2614.566 | 2693.003 | 2773.7931 | 2857.0068 | 2942.7171 |  | 13881.0859
| Existing: 2 A/O I -Env Sci (Program Managers), total of 0.1 FTE year 1 only, with 3% 2024 salary increase | 7484.5858 | 0 | 0 | 0 | 0 |  | 7484.5858
| TOTAL FRINGE BENEFITS | 74549.8211 | 133014.5269 | 137004.9627 | 141115.1116 | 145348.565 | 0 | 631032.9873
| TOTAL PERSONNEL + FRINGE BENEFITS | 266688.5353 | 475835.4726 | 490110.5368 | 504813.8529 | 519958.2685 | 450000 | 2257406.666
Travel
Vehicle travel for community meetings, site visits x 4 staff; 12-13 trips each for 18 days per year
| Mileage for local travel (50 trips * 400 miles/trip at $0.66/mi) | 13200 | 13596 | 14003.88 | 14423.9964 | 14856.7163 |  | 70080.5927
| Airfare - ($350/roundtrip x 4 people x 1 trip) + ($700/roundtrip x 4 people x 2 trips) | 7000 | 7210 | 7426.3 | 7649.089 | 7878.5617 |  | 37163.9507
| Luggage Fees - $25 per flight @ 12 flights/year | 300 | 309 | 318.27 | 327.8181 | 337.6526 |  | 1592.7407
| Hotel - (6 local nights/staff * 4 staff * $157/night) + (8 non-local nights/staff * 4 staff * $250/night) | 12200 | 12566 | 12942.98 | 13331.2694 | 13731.2075 |  | 64771.4569
| Per Diem - [(50 local trips x 1.5 days/trip) + (11 non-local travel days/staff * 4 staff)] * $59/day | 7021 | 7231.63 | 7448.5789 | 7672.0363 | 7902.1974 |  | 37275.4425
| Taxi - 120 miles/traveler * 4 travelers/trip * 3 trips * $0.66/mile | 950.4 | 978.912 | 1008.2794 | 1038.5277 | 1069.6836 |  | 5045.8027
| Parking - ($20 per non-local travel day * 11 non-local travel days/staff * 4 staff) | 880 | 906.4 | 933.592 | 961.5998 | 990.4478 |  | 4672.0395
| TOTAL TRAVEL | 41551.4 | 42797.942 | 44081.8803 | 45404.3367 | 46766.4668 |  | 220602.0257
Equipment
| 2023 Ford F-150 Lightning PRO CrewCab 4WD or similar EV, 50% (to be split with CTI measure) | 29340 | 0 | 0 | 0 | 0 |  | 29340
| TOTAL EQUIPMENT | 29340 | 0 | 0 | 0 | 0 |  | 29340
Supplies
| Level 2 Vehicle Charger, including installation, 50% (to be split with CTI measure) | 2450 | 0 | 0 | 0 | 0 |  | 2450
| Laptop computer and docking station x 4; periodic replacement | 8800 | 0 | 2332 | 2398 | 0 |  | 13530
| Computer supplies x 4 (mouse, keyboard, monitor, cables, connectors, webcam, etc.), periodic replacement | 3008 | 0 | 797.12 | 0 | 892.7744 |  | 4697.8944
| iPhone 15 (for quality camera) x 4, 2 replacements | 3320 | 0 | 0 | 1809.4 | 0 |  | 5129.4
| Flipcharts and meeting supplies (tables; banners; educational material) | 1300 | 1000 | 500 | 235 | 235 |  | 3270
| Paper Supplies/outreach material | 1240 | 1240 | 500 | 250 | 250 |  | 3480
| Communication Supplies (Fax, Mail, Xerox) | 1300 | 2000 | 1000 | 198 | 198 |  | 4696
| Clipboards, Notepads, Notebooks, Binders | 480 | 360 | 185 | 0 | 0 |  | 1025
| TOTAL SUPPLIES | 21898 | 4600 | 5314.12 | 4890.4 | 1575.7744 |  | 38278.2944
Contractual
| Consultant: Community, Tribal nations, and stakeholder outreach and engagement with focus on LIDAC | 48000 | 23000 | 18000 | 16000 | 10000 |  | 115000
| Fleet advisor for approximately 33 fleet assessments | 0 | 175000 | 175000 | 175000 | 175000 | 50000 | 700000
| Technical analysis to support measuring and tracking progress towards achieving established targets, including calculating and reporting reductions in GHG, NOX, SO2, PM2.5, and PM10 based on VMT and emission factors; technical analysis to assess community and workforce benefits | 50000 | 25000 | 50000 | 25000 | 50000 |  | 200000
| Third-party reviewer(s) for Guaranteed Energy Savings Performance Contracts (ESPC), approximately 10 per year | 200000 | 200000 | 200000 | 200000 | 200000 |  | 1000000
| TOTAL CONTRACTUAL | 298000 | 423000 | 443000 | 416000 | 435000 |  | 2015000
OTHER
| Participant Support Costs: approximately 210 Electric School Bus Charging Stations - (estimated $46,000 each; $32,200 with tax credit) | 0 | 1690500 | 1741215 | 1793451.45 | 1847254.9935 | 375000 | 7072421.4435
| Participant Support Costs: approximately 100 Electric School Bus Vouchers (estimated $420,000 each; $380,000 with tax credit) | 0 | 9500000 | 9785000 | 10078550 | 10380906.5 | 781250 | 39744456.5
| Subaward to NM Dept. of Workforce Solutions to support workforce development boards to address job training and readiness | 200000 | 200000 | 200000 | 200000 | 200000 |  | 1000000
| Per FTE costs - payroll & financial software subscription, phone service, IT services including email, PowerPlatform, internet, software x 4; (6 months year 1 due to time needed to create and hire for positions) | 12604 | 25964.24 | 26743.1672 | 27545.4622 | 28371.8261 |  | 121228.6955
| Video meeting capability: 1 conferencing system with 360-degree camera, speakers, mics, 1 projector | 1700 | 0 | 0 | 0 | 0 |  | 1700
| Full video conferencing license, 4 hosts | 480 | 988.8 | 1018.464 | 1049.0179 | 1080.4885 |  | 4616.7704
| Public Survey License, 3 users | 1350 | 2781 | 2864.43 | 2950.3629 | 3038.8738 |  | 12984.6667
| Project Management Software License, 4 users | 408 | 816 | 840.48 | 865.6944 | 891.6652 |  | 3821.8396
| TOTAL OTHER | 216542 | 11421050.04 | 11757681.5412 | 12104411.9874 | 12461544.3471 |  | 47961229.9157
| TOTAL DIRECT | 874019.9353 | 12367283.4546 | 12740188.0782 | 13075520.577 | 13464844.8567 |  | 52521856.9017
Indirect Costs | Indirect Costs
|  | 93874.3644 | 167494.0864 | 172518.9089 | 177694.4762 | 183025.3105 |  | 794607.1464
| TOTAL INDIRECT | 93874.3644 | 167494.0864 | 172518.9089 | 177694.4762 | 183025.3105 |  | 794607.1464
TOTAL FUNDING |  | 967894.2997 | 12534777.5409 | 12912706.9872 | 13253215.0532 | 13647870.1672 | 0 | 53316464.0482
Y= year
Where appropriate, costs are adjusted for inflation

## CTI Timeline Milestones
New Mexico Clean Trucks Incentive Program Implementation Timeline and Milestones: October 2024 through December 2029
Calendar Year |  | 2024 |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
Calendar Year Quarters |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Quarters since award |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Activities and Milestones, indicated by an '*'
1 | Submit Application | *
2 | Receive Award | bar: 2024 Q4 1
3 | Hire a Program Manager and 3 Program Coordinators | bar: 2024 Q4 1
4 | Selection of a fleet advisor through competitive procurement | bar: 2024 Q4 1
5 | Submit Quality Assurance Program Plan (QAPP) to EPA | bar: 2024 Q4 1
6 | Preparation program manual, application, training materials, terms and conditions for participating dealerships and station installers, and promotional materials with outreach around these materials
7 | Provide Workforce Solutions Department funding for job development | bar: 2025 Q1 2
8 | Certification of medium and heavy-duty vehicle vendors and infrastructure installers
9 | Outreach, education, community and fleet engagement including program design, forms and manuals, opportunities
10 | Launch Technical Assistance Office | bar: 2025 Q1 2
11 | Advertise application requirements and solicit applications
12 | Application deadline for each round | bar: 2025 Q3 4; 2026 Q3 8; 2027 Q3 12; 2028 Q3 16
13 | Review applications, determine eligibility, prioritize applicants through Title I focus, select awards, and enter into agreements with project sponsors
14 | Fleet Advisor provides technical assistance to project awardee
15 | Disburse participant support costs to vehicle and installation vendors
16 | Charging installations completed and ZET delivered | bar: 2026 Q3 8; 2027 Q3 12; 2028 Q3 16; 2029 Q3 20
17 | After each evaluation performed, revise program manual, promotional materials, and application as needed in response to participant and community feedback
18 | Seek additional incentive funding
19 | Track and review performance measures
20 | Submit semiannual reports, including performance measures | bar: 2025 Q2 3; 2025 Q4 5; 2026 Q2 7; 2026 Q4 9; 2027 Q2 11; 2027 Q4 13; 2028 Q2 15; 2028 Q4 17; 2029 Q2 19
21 | Submit final report | bar: 2029 Q4 21

## ECO School Time Milestones
New Mexico ECO Schools Implementation Timeline and Milestones: October 2024 through December 2029
Year |  | 2024 |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
Quarter |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Quarters since award |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Activities and Milestones, indicated by an '*'
1 | Submit Application | *
2 | Receive Award | bar: 2024 Q4 1
3 | Hire a Program Manager and 2 Program Coordinators | bar: 2024 Q4 1
4 | Selection of a fleet advisor through competitive procurement | bar: 2024 Q4 1
5 | Selection of energy savings third party reviewers | bar: 2024 Q4 1
6 | Submit Quality Assurance Program Plan (QAPP) to EPA | bar: 2024 Q4 1
7 | Provide Workforce Solutions Department funding for job development | bar: 2025 Q1 2
8 | Preparation of a program manual, application, training materials, terms and conditions for participating dealerships and station installers, and promotional materials with outreach around these materials
9 | Certify school bus vendors and infrastructure installers
10 | Outreach, education, community and school engagement including program design, forms and manuals, opportunities
11 | Launch of Technical Assistance Office | bar: 2025 Q1 2
12 | Advertise application requirements and solicit applications
13 | Application deadline for each round | bar: 2025 Q3 4; 2026 Q3 8; 2027 Q3 12; 2028 Q3 16
14 | Review applications, determine eligibility, prioritize applicants through Title I focus, select awards, and enter into agreements with project awardees
15 | Fleet Advisor provides technical assistance to project sponsors
16 | Schools work with ESCOs on energy savings performance contracts
17 | Disburse PSC to Vehicle Vendor and Installation Vouchers
18 | Charging Installations Completed and ZEB Delivered | bar: 2026 Q3 8; 2027 Q3 12; 2028 Q3 16; 2029 Q3 20
19 | After each evaluation performed, revise program manual, promotional materials, and application as needed in response to participant and community feedback
20 | Seek additional incentive funding
21 | Track and review performance measures
22 | Semiannual Reporting, including performance measures | bar: 2025 Q2 3; 2025 Q4 5; 2026 Q2 7; 2026 Q4 9; 2027 Q2 11; 2027 Q4 13; 2028 Q2 15; 2028 Q4 17; 2029 Q2 19
23 | Final Reporting | bar: 2029 Q4 21

## Measure 3 Budget (hidden)
Detailed Budget Table
This Excel Workbook is provided to aid applicants in developing the required budget table(s) within the budget narrative.
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 |  | TOTAL
Direct Costs | Personnel
[7 empty] | 450000 | 0
0
0
| TOTAL PERSONNEL | 0 | 0 | 0 | 0 | 0 | 450000 | 0
Fringe Benefits
0
0
0
| TOTAL FRINGE BENEFITS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
0
0
[7 empty] | 2000 | 0
[7 empty] | 250 | 0
[7 empty] | 2250 | 0
[7 empty] | 1243 | 0
[7 empty] | 225 | 0
[7 empty] | 400 | 0
[7 empty] | 1638 | 0
| TOTAL TRAVEL | 0 | 0 | 0 | 0 | 0 |  | 0
Equipment
0
0
| TOTAL EQUIPMENT | 0 | 0 | 0 | 0 | 0 |  | 0
Supplies
[7 empty] | 5000 | 0
0
| TOTAL SUPPLIES | 0 | 0 | 0 | 0 | 0 |  | 0
Contractual
0
[7 empty] | 22500000 | 0
[7 empty] | 75000000 | 0
0
0
| TOTAL CONTRACTUAL | 0 | 0 | 0 | 0 | 0 |  | 0
OTHER
[7 empty] | 375000 | 0
[7 empty] | 781250 | 0
[7 empty] | 2083335 | 0
0
0
0
| TOTAL OTHER | 0 | 0 | 0 | 0 | 0 |  | 0
| TOTAL DIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
Indirect Costs | Indirect Costs
0
0
| TOTAL INDIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL FUNDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Measure 4 Budget (hidden)
Detailed Budget Table
This Excel Workbook is provided to aid applicants in developing the required budget table(s) within the budget narrative.
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 |  | TOTAL
Direct Costs | Personnel
[7 empty] | 450000 | 0
0
0
| TOTAL PERSONNEL | 0 | 0 | 0 | 0 | 0 | 450000 | 0
Fringe Benefits
0
0
0
| TOTAL FRINGE BENEFITS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
0
0
[7 empty] | 2000 | 0
[7 empty] | 250 | 0
[7 empty] | 2250 | 0
[7 empty] | 1243 | 0
[7 empty] | 225 | 0
[7 empty] | 400 | 0
[7 empty] | 1638 | 0
| TOTAL TRAVEL | 0 | 0 | 0 | 0 | 0 |  | 0
Equipment
0
0
| TOTAL EQUIPMENT | 0 | 0 | 0 | 0 | 0 |  | 0
Supplies
[7 empty] | 5000 | 0
0
| TOTAL SUPPLIES | 0 | 0 | 0 | 0 | 0 |  | 0
Contractual
[7 empty] | 5106000 | 0
[7 empty] | 22500000 | 0
[7 empty] | 75000000 | 0
0
| TOTAL CONTRACTUAL | 0 | 0 | 0 | 0 | 0 |  | 0
Other
[7 empty] | 375000 | 0
[7 empty] | 781250 | 0
[7 empty] | 2083335 | 0
0
0
0
| TOTAL OTHER | 0 | 0 | 0 | 0 | 0 |  | 0
| TOTAL DIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
Indirect Costs | Indirect Costs
0
0
| TOTAL INDIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL FUNDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Measure 5 Budget (hidden)
Detailed Budget Table
This Excel Workbook is provided to aid applicants in developing the required budget table(s) within the budget narrative.
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 |  | TOTAL
Direct Costs | Personnel
[7 empty] | 450000 | 0
0
0
| TOTAL PERSONNEL | 0 | 0 | 0 | 0 | 0 | 450000 | 0
Fringe Benefits
0
0
0
| TOTAL FRINGE BENEFITS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
0
0
[7 empty] | 2000 | 0
[7 empty] | 250 | 0
[7 empty] | 2250 | 0
[7 empty] | 1243 | 0
[7 empty] | 225 | 0
[7 empty] | 400 | 0
[7 empty] | 1638 | 0
| TOTAL TRAVEL | 0 | 0 | 0 | 0 | 0 |  | 0
Equipment
0
0
| TOTAL EQUIPMENT | 0 | 0 | 0 | 0 | 0 |  | 0
Supplies
[7 empty] | 5000 | 0
0
| TOTAL SUPPLIES | 0 | 0 | 0 | 0 | 0 |  | 0
Contractual
[7 empty] | 5106000 | 0
[7 empty] | 22500000 | 0
[7 empty] | 75000000 | 0
0
| TOTAL CONTRACTUAL | 0 | 0 | 0 | 0 | 0 |  | 0
OTHER
[7 empty] | 375000 | 0
[7 empty] | 781250 | 0
[7 empty] | 2083335 | 0
0
0
0
| TOTAL OTHER | 0 | 0 | 0 | 0 | 0 |  | 0
| TOTAL DIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
Indirect Costs | Indirect Costs
0
0
| TOTAL INDIRECT | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL FUNDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sample Budget 1 (hidden)
Detailed Budget Table
BUDGET BY YEAR
COST-TYPE | CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | TOTAL
Direct Costs | Personnel
| Project Manager @ $80,000/yr, .5 FTE, with salary increase | 40000 | 42500 | 45000 | 47500 | 50000 | 225000
| Project Staff @ $60,000 .5 FTE each year with salary increase | 30000 | 32500 | 35000 | 37500 | 40000 | 175000
| TOTAL PERSONNEL | 70000 | 75000 | 80000 | 85000 | 90000 | 400000
Fringe Benefits
| Full-time Employees @ 17% of salary | 11900 | 12750 | 13600 | 14450 | 15300 | 68000
0
0
| TOTAL FRINGE BENEFITS | 11900 | 12750 | 13600 | 14450 | 15300 | 68000
Travel
Travel for conference and workshop presentations:
| Airfare - $400 roundtrip @ 1 roundtrip per year | 400 | 400 | 400 | 400 | 400 | 2000
| Luggage Fees - $25 per flight @ 2 flights per year | 50 | 50 | 50 | 50 | 50 | 250
| Hotel - $150 per day @ 3 days per year | 450 | 450 | 450 | 450 | 450 | 2250
| Per Diem - $71 per day @ 3.5 days per year | 248 | 248 | 248 | 248 | 248 | 1240
| Taxi - $45 per year | 45 | 45 | 45 | 45 | 45 | 225
| Parking - $20 per day @ 4 days per year | 80 | 80 | 80 | 80 | 80 | 400
| Mileage for local travel (500 miles per year at $0.655/mi) | 328 | 328 | 328 | 328 | 328 | 1640
| TOTAL TRAVEL | 1601 | 1601 | 1601 | 1601 | 1601 | 8005
Equipment
| 2 Building Thermal Imagers @ $9,000 each | 18000 |  |  |  |  | 18000
0
| TOTAL EQUIPMENT | 18000 | 0 | 0 | 0 | 0 | 18000
Supplies
| 1 Laptop Computer @ $2,500 each | 2500 | 0 | 0 | 0 | 0 | 2500
0
| TOTAL SUPPLIES | 2500 | 0 | 0 | 0 | 0 | 2500
Contractual
| Contractor to perform 30 energy assessments per year at industrial facilities. Assumes 740 hours per assessment (pre-visit analysis, site visit, post-visit analysis, report with recommendations) @ $46/hr | 1021200 | 1021200 | 1021200 | 1021200 | 1021200 | 5106000
| Contract for 10 small or medium-scale projects per year at industrial facilities (renewable energy, energy storage, energy efficiency, electrification, or energy planning). Assumes average cost $450,000/project | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 22500000
| Contract for 5 large-scale energy efficiency or decarbonization demonstration projects per year at industrial facilities (e.g., industrial heat pumps). Assumes average cost $3 million/project | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 75000000
0
| TOTAL CONTRACTUAL | 20521200 | 20521200 | 20521200 | 20521200 | 20521200 | 102606000
OTHER
| Participant Support Costs: Stipends for 2 Summer Interns | 8000 | 8000 | 8000 | 8000 | 8000 | 40000
| Participant Support Costs: Industrial Retrofit Rebates, 50 facilities/yr @ $200,000 each | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
0
| TOTAL OTHER | 10008000 | 10008000 | 10008000 | 10008000 | 10008000 | 50040000
| TOTAL DIRECT | 30633201 | 30618551 | 30624401 | 30630251 | 30636101 | 153142505
Indirect Costs | Indirect Costs
0
0
| TOTAL INDIRECT | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FUNDING |  | 30633201 | 30618551 | 30624401 | 30630251 | 30636101 | 153142505