Pechanga Band of Indians Emissions Reduction from Tribal Utility Operations

EPA CPRG General Fund Implementation Application Workplan

The Pechanga Band of Indians (Pechanga) is deeply committed to continuously improving our environmental footprint.  We appreciate this EPA CPRG program which will assist us in protecting our beautiful earth from the devastating effects of climate change.

Section 1: Overall Project Summary and Approach

As noted in our Priority Climate Action Plan (PCAP), Pechanga has already taken many steps toward reducing our climate emissions. We have hired a sustainability manager for our commercial operations who has implemented many efficiency measures, developed plans for energy efficiency at our government center, planned new facilities with energy efficient systems, developed solar and battery installations and plans for our residential areas, added 1.3MW of utility scale solar on our garage rooftop, installed 1 MW (4MWH) of battery storage, added over 100 electric vehicle chargers and employed a 4.6MW cogeneration plant.

Tribal goals include environmental sustainability, energy self-sufficiency, energy sovereignty, lowering costs, and energy resiliency.  Tribally stated cultural standards require efficiently using then reusing waste resources.

Pechanga is the only Indian Tribe in California with a fully integrated tribally owned and operated utility, Pechanga Western Electric (PWE), serving its reservation. To meet PWE’s current power need of up to 18MW, PWE buys power from the California Independent System Operator (CAISO) grid, generates up to 5.9MW of electricity on the Reservation from a 4.6MW natural gas cogeneration plant and a 1.3MW solar system, then distributes the electricity on its tribally owned distribution system to tribal and non-tribal loads and charges its own utility rates which are significantly less than California utility rates.  PWE can also operate as a microgrid (independently and without grid power support) in times of emergency using 16MW of diesel backup generators and a 1MW/4MWh battery system.

PWE has a Memorandum of Understanding (MOU) with the Pechanga Development Corporation (PDC).  PDC is another branch of the Pechanga government formed to help achieve the goal of tribal self-sufficiency.  PDC was created for the purpose of economic development and improving the business, financial and general welfare of the Pechanga Tribe.  The PDC is led by a five-member board of directors that is elected to two-year terms by Pechanga Citizens.  PDC’s first economic development venture was the Pechanga Entertainment Center, which opened in July 1995 with 135 employees.  Known today as the Pechanga Resort & Casino (PRC), the operation has developed into the second largest private employer in Riverside County with more than 4,000 Team Members.  In addition to the resort and casino, PDC also manages the Pechanga RV Park, the Pechanga Gas Station, and several land holdings throughout Southern California. PDC’s power operations have a current full-time staff of 14 employees, most of whom are veterans from Naval vessels who operate and maintain the existing cogeneration plant among other facilities responsibilities. The new measurers will require an additional 9 operators. PDC will operate and maintain the new measures described in this application. PWE and PDC are in the process of updating their MOU to address utility related issues and their respective roles and responsibilities within the Pechanga government.

The goal of this application is to reduce the emissions from Pechanga’s utility operations. Two of the three measures we propose, though encouraged by EPA, have no other known available grant funding because they relate to fossil fuel activities (cogeneration and diesel efficiency).  Our PCAP review of our emissions was limited to our utility function. The PCAP estimated our emissions of CO2 related to our utility function equals 23,539 metric tons for internal natural gas generation and 13,898 metric tons related to market purchases for a total of 37,437 metric tons. In addition, there are significant emissions from our diesel generators, which we will further document in our Comprehensive Climate Action Plan. We are therefore prioritizing measures which reduce our emissions from our utility function and have no other known grant funding available. Other grant applications are being developed to address transportation, residential, governmental and other climate impacts.

With this grant, we seek to build on our existing success by adding the next phases of equipment to our power plant, and to improve the efficiency of the existing equipment in manners that will continue our dedication to reducing our emissions and environmental sustainability. Our existing experience with battery storage and with our cogeneration plant has yielded excellent results in saving emissions, costs and improving efficiency. Results from a 2015 study by our Contract Engineering Firm, Elen Consulting, Inc. of our existing 4.6MW cogeneration system show our cost savings and therefore our reduced power purchases, as summarized below:

- Description of GHG Reduction Measures

The goal of this application is to reduce the emissions from PWE’s utility operations by focusing on the following utility scale related electricity generation measures:

- Installation of a 5MW Natural Gas Cogeneration Turbine and associated 4MW Natural Gas Cogeneration Caterpillar Generators (Cogen Plant): See Pechanga PCAP, Page 20. These two combined heat and power cogeneration generators will work together to support utility external and internal power fluctuations. Cogeneration meets tribal cultural standards of efficiently using then reusing waste resources. The Cogeneration Plant will meet the goals of the CPRG program by:

  - Offsetting dirtier wholesale energy purchases from the CAISO market.

  - Reusing waste heat/steam to heat and cool tribal facilities, eliminating the need for other heating and cooling systems.

  - Offsetting gas boilers which heat resort and recreation center swimming pools.

See the below chart that show use of thermal energy generated by the proposed Cogeneration facility:

Cogen Plan Features, Tasks and Milestones:

Our assumptions about this project are described here. Pechanga currently owns a 5.85 gross/4.6 MW net natural gas fired Cogeneration Plant (2 SunPower turbines with other associated equipment), which is located at the Pechanga Resort at the South Central Power Plant and is managed by PDC. We intend this Cogen Plant measure to be a second phase of our existing plant.

Cogeneration, through combined heat and power (CHP), is the simultaneous production of electricity with the recovery and utilization of steam to heat or cool. According to the EPA, CHP’s key roles in a clean energy market are to (1) reduce emissions while the grid transitions towards cleaner energy; (2) support solar and wind power resources in microgrids to increase on-site reliability and resiliency; and (3) reduce emissions in sectors that are hard to decarbonize. EPA also indicates that when evaluated against comparable separate heat and power options, CHP reduces emissions of greenhouse gases and other air pollutants by avoiding the need for grid-based electricity generation, transmission, and distribution, and an on-site boiler.

CHP plants significantly reduce carbon emissions and cogeneration is a highly efficient form of energy conversion. A conventional 1MW CHP system would produce about half (42,000 tons of the annual CO2 emissions that grid based electricity and a conventional boiler would, assuming national average marginal grid emissions rates.

PWE has completed negotiations on new Wholesale Distribution Access Tariff agreements with Southern California Edison which allow PWE to export this power, allowing the cogen power to be counted toward PWE’s Resource Adequacy needs.

Pechanga has estimated its load growth in the next 8 years to be between 7.25 MW and 14.8 MW. This load growth is resulting from a new school, new commercial ventures, added land base for housing and other development, tribal government growth and significant new electric vehicle charging, both for tribal members, tribal employees, and for PRC guests. These projected loads versus the current generation resources indicates that if new on-reservation generation is not added, power will be required by PWE from market resources through purchases from CAISO. As shown in the graphic (as of February, 2024), CAISO’s largest resources is natural gas. To avoid making market purchases of power to meet load growth at fluctuating rates that has the likelihood of being serviced by less efficient natural gas, or potentially by imports that are also often not renewable, tribal investment in new CHP facilities, with the latest technology and the efficiencies of using the waste heat from the CHP for other purposes, is projected to improve the Tribe’s emissions. While it is recognized that there may be some emissions from a new CHP, added solar and batteries can mitigate this generation. Tribal engineers recommend an additional 5 MW of long-term CHP, 4MW of CHP short and long-term peak generators and 2-4 MW of battery storage in the short term.

This measure will involve the purchase and installation of a second CHP facility, which will reduce purchased power generated from non-renewable sources. The proposed new Pechanga Cogen Plant plan will provide enough thermal energy to cover current output of not only existing pool heaters, but also existing steam boilers located in the Tribe’s South Central Power Plant. The Cogen Plant project will also produce chilled water and offset energy used by electrical chillers. Additionally, it will generate electrical energy and reduce carbon emissions from the utility power plants.

Proposed cogeneration equipment includes prime-movers (engine/generators), engine waste-heat recovery equipment and emissions control equipment. We are proposing one 4.6MW gas turbine (5MW nominal) and (2) 2MW gas generators for total of approximately 9MW of power cogeneration capacity. These pieces of equipment work together for the greatest efficiency of the Cogen Plant and operate as one facility. The turbine is intended to run continuously at its full capacity. The gas generators are intended to follow the load and ramp up or down based on the actual power demand. See the following initial design depictions completed in 2023 which shows the new turbine/gas generators and related equipment in bold, next to the existing turbine in gray:

The electrical energy generated by cogeneration will offset facility utility electrical energy demand. The thermal recovery from generators will be recovered by the Heat Recovery Steam Generator (HRSG) in form of 120 PSIG saturated steam which will be piped to the existing steam distribution system which serves the Pechanga Resort and used to supply facility loads. As shown below, our engineers have calculated a 64% efficiency of the proposed Cogen Plant based on the anticipated operation conditions, (electrical energy generation, gas consumption, operation hours, etc.).

The annual existing 4.6MW cogeneration facility steam load listed above represents only 40% of the annual available HRSG output, so additional waste heat consumption is needed at the Pechanga Resort to meet minimum Federal Energy Regulatory Commission (FERC) requirements as cogeneration Qualified Facility.  A heat-driven chiller will provide additional waste heat consumption to both meet minimum FERC requirements.

An annual proforma of the new 5MW cogeneration turbine operations is provided in the table below reflecting anticipated full electrical & thermal utilization of the cogeneration system.

The 64% anticipated efficiency greatly exceeds 30%-35% efficiency of the typical electrical utility power plant.

Major equipment of the proposed cogeneration facility includes Gas Generators, Heat Exchanger and Absorption chiller. See the below process flow diagram.

Pechanga Cogeneration Plant Process Flow and Energy Metering Diagram

Cogen Associated Risks

This is a low-risk project, as it is the second phase of an existing successful project.

The greatest risk known at this time is the ability to obtain timely delivery of equipment due to supply chain issues and competition among other entities for desired equipment.  This risk is mitigated as much of the underlying needed equipment, staff and technology is in place.  PWE has on hand many of the electrical switches, and some of the other electrical equipment needed for the project. This risk could lead to a delay in the project by up to 1 year.

Milestones

Milestones for Obtaining Implementing Authority include General Council Approval, SCE Interconnection Agreement similar to the one we currently have, and CAISO Interconnection Agreement which allows CAISO to “see” the equipment for Resource Adequacy purposes.

| Activity | Length of Time | If begin now Completion |
| --- | --- | --- |
| Design | 8-9 months | 12/2024 |
| Procurement | 2-3 months | 3/2025 |
| Start Construction: Underground Utilities |  | 9/2024 |
| Start Construction: Building Addition |  | 2/2025 |
| Construction | 24 months | Substantial completion 3/2027 |
| Start-up and Commissioning | 3 months | 6/2027 |

- Installation of 2MW (4MWh) of Battery Backup to the Cogeneration: See Pechanga PCAP. Page 18. The Battery Backup is a further efficiency for the Cogeneration Plant.  Battery Backup meets the goals of the CPRG program by:

  - Reducing our need to run diesel generators.

  - Make our Cogeneration Plant even more efficient.

  - Reduce our wholesale purchases from the CAISO market.

Battery Backup Features

Our assumptions about this project are described here. In addition to our existing 1MW of solar photovoltaic on our East parking structure, Pechanga is now installing an additional 1 MW/4MWH battery storage system near the Great Oak Substation. The system is scheduled to be completed in 2024. Batteries allow us to store “free” solar energy or charge the batteries from the existing cogeneration plant when our loads are low or from grid power when market prices are low (generally late at night or during sunny hours). This will allow us to offset 1 MW/4MWH of purchases when prices are high (generally in late afternoon). Storing electricity can provide indirect environmental benefits. For example, electricity storage can be used to help integrate more renewable energy into the electricity grid. Electricity storage can also help generation facilities operate at optimal levels and reduce use of less efficient generating units that would otherwise run only at peak times. Further, the added capacity provided by electricity storage can delay or avoid the need to build additional power plants or transmission and distribution infrastructure.

PWE wishes to purchase an additional 2 MW/4MWH batteries in conjunction with our new Cogen Plant to improve existing system reliability and reduce purchased power generated by non-renewable sources. The batteries assist the CHP in avoiding market purchases and can make the most of solar power generated when loads are lower than generation.

Benefits of 2 MW of additional battery storage include:

- The batteries assist the CHP in avoiding market purchases,

- Batteries make the most of solar power generated when loads are lower than generation.

- Batteries meet immediate needs for capacity.

- Batteries meet the goal of self-sufficiency.

- The Tribe has experience with battery storage.

Installing Battery Energy Storage System (BESS) will allow peak shaving and leveling the minimum and maximum electrical loads. This will help better utilize the proposed cogeneration equipment.

Operating this BESS in 50%-100% of its full output range would increase the minimum and reduce the maximum campus loads by approximately 500kW while maintaining an adequate reserve of standby energy. The estimated minimum net load then will be 3,600 kW which will allow to raise the turbine-generator power output during the low load conditions to 85%-95%. Adding a second 2,000kW/4,000kWh BESS system and using it for electrical load leveling will bring the minimum and maximum net loads to the 5,000kW-6,000kW average load range which will allow continuous operation of all on-site cogeneration units at nearly full electrical load and optimum efficiency.

Battery Associated Risks

This is a low-risk project, as it is the second phase of an existing successful Battery storage project which will be located with the other batteries near the Great Oaks Substation on the Pechanga Reservation. Potential negative impacts include use of raw materials such as lithium and lead and can pose environmental hazards if not properly disposed.

Another risk known at this time is the ability to obtain timely delivery of equipment due to supply chain issues and competition among other entities for desired equipment.  This risk is mitigated as much of the underlying needed equipment, staff and technology is in place.  PWE has on hand many of the electrical switches, and some of the other electrical equipment needed for the project. This risk could lead to a delay in the project by up to 1 year.

Battery Milestones

Milestones for Obtaining Implementing Authority include Tribal Council approval which was previously authorized by the General Membership. Some coordination with Southern California Edison and CAISO will be needed.

| Activity | Length of Time | If begin now Completion |
| --- | --- | --- |
| Design | 3-6 months | 8/2024 |
| Procurement | 1-2 months | 10/2024 |
| Start Construction: |  | 10/2024 |
| Construction | 6 months | Substantial completion 4/2025 |
| Start-up and Commissioning | 1 month | 5/2025 |

- Improving the Efficiency of our 15.25MW of Diesel Generators with Hydrogen Technology: See Pechanga PCAP, Page 15. Installing “Boost Box” hydrogen systems (Boost Box) on our diesel generators will meet the goals of the CPRG program by reducing our use of diesel and will otherwise make the diesel generators more efficient.

Diesel Generator – Hydrogen Efficiency Features, Tasks and Milestones:

PWE can draw on 14 MW of emergency diesel generation operated by PRC. An additional 1.25 MW of emergency diesel generators are located at various buildings near the government center. This measure includes adding “BoostBox” technology developed by Hydrogen On Demand Technologies, a Silicon Valley based company, (HODT) to the Tribe’s existing Diesel Generators to improve efficiency and reduce emissions.

BoostBox HODT is a Proton Exchange Membrane Cell Technology (PEM Cell) company that produces hydrogen on-demand, on-site to improve the efficiency of existing installations of diesel engines and generators. Hydrogen is produced on demand within the equipment only while the engines are running, so no hydrogen is ever stored. The system uses no hazardous chemicals; hydrogen is created from only distilled water. The hydrogen gas is never under any pressure and the system will not operate if the engines are shut down. Hydrogen gas represents far less than 1% of the total airflow when introduced into an engine. BoostBox HDOT generates hydrogen gas on board which is added to the engine inlet air via the air intake. The hydrogen gas then contributes to the fuel combustion, acting as a catalyst; not to be confused as an additional fuel source or fuel additive. The hydrogen ensures that the fuel is burned more completely within the engine.

This technology will improve the torque of the diesel generator engines, reaching max torque faster at lower RPM. HDOT  has developed a comprehensive and durable technology platform which reduces fuel consumption and harmful emissions for diesel engines, custom configured to the engine’s unique requirements based on engine size, configuration, and application specific parameters. By increasing combustion efficiency, engines produce less particulate matter (soot), less nitrous oxide emissions (NOx) and generally run cleaner. With hydrogen assist, the burned fuel now exits the exhaust stack in the cleanest possible form, meaning that the engines will accumulate fewer carbon deposits. Components will be subject to less wear and tear, yielding longer service life when compared to historical maintenance records. More complete combustion also means that more energy is extracted from fuel. Hydrogen assist technology provides a fuel economy increase of up to and often above 10% from baseline, when compared to standard fuel engines of all types. These factors combine to create savings across diesel powered systems. Cleaner engines and reduced carbon buildup lead to more reliable operations and increased time between maintenance intervals. This delivers a bonus of extended engine longevity. Given that hydrogen burns approximately ten times faster than any fossil fuel, the combustion characteristics in each cylinder stroke will change ensuring the fuel will burn faster, more completely and more efficiently. The system improves the combustion burn efficiency up to 95%, producing increased energy and torque while allowing less than 5% of the stored energy potential (power and torque) to escape as partially burned hydrocarbons into the exhaust system. The results of this enhanced / enriched burn will be significant reductions in both fuel usage and emissions. This technology will improve fuel efficiency by an average of 10% and make the existing diesel cleaner, which will result in the reduction of greenhouse gas emissions. Historical testing has proven that when the BoostBox HDOT systems are deployed, greenhouse gas emissions are quantifiably reduced, as follows.

| Estimate of Quantifiable GHG Emissions Reductions | - Reduces CO emissions by 35%+ - Reduces CO2 emissions by 10%+ - Reduces NOx emissions by up to 75% - Reduces particulate emissions (opacity) by between 65-85%. |
| --- | --- |
| Key Implementing Agency or Department | PRC and PWE will contract with BoostBox HDOT to develop the project and incorporate the technology. |
| Implementation Schedule/Milestones | Month 1-6 - Design of devices for each generator. Month 6-12 – Device manufacture and installation. |
| Expected Geographic Location | To be installed on the Tribe’s existing diesel generators at the Casino and government center. |
| Milestones for Obtaining Implementing Authority | Subject to Tribal Council approval. |
| Intersection with Other Funding Sources | - EPA CRPG Implementation Grant - EPA Community Change Grant (not yet applied for) |
| Metrics for Tracking Progress | Boostbox data tools, Pechanga’s Environmental Protection Office, PRC generator inspections and run data. |
| Quantitative Cost Estimates (Based on Proposal from HODT) | Configuration and Engineering $310,000 Equipment $1,954,000 Installation $120,000 Total: $2,384,000 |

Diesel generators are routinely inspected, run and maintained by the PDC power plant operators. We expect an annual report on the effectiveness, emissions, benefits and downsides of the operations of the diesel generators after the systems are installed.  The initial product testing will be comprehensive and sufficient to prove product performance with respect to emissions reduction, and reliability with real-world testing using actual diesel motors in normal operational environments to determine actual long haul fuel savings.  Full datasets and operational data from the initial on-board installations will be available for review by all parties, and application optimized algorithms will be developed to address additional requirements.

Additionally, the system features advanced processing and remote data collection technologies which enable HODT to remotely support the product and provide an advanced degree of service for the lifetime of the system. The platform also allows operators within end user’s base to interact with the operational data and fully realize the system benefits. This Industry 4.0 internet connected initiative begins with the system installation and encompasses initial training/commissioning. It includes an in-force service contract across the life of the product with data analysis and report generation.

The benefits of this measure are that the technology is innovative and makes diesel generators more efficient. A con is that because the diesel generators are used only for standby, the price per ton of CO2 is higher and payback time is longer, and the emissions reduced is low in the short-term. Pechanga does not have experience with this product, but the technology has been successfully implemented in other areas.

BoostBox HODT Diesel Generator Efficiency Risks

The main risk is that while this technology is tested and verified, it is not well known.  This risk is mitigated by the data tools and expertise that come with the purchase of the equipment and technology.  We do not expect the GHG emission reductions to be affected by this risk.

Diesel Generator Efficiency Milestones

| Activity | Length of Time | If begin now Completion |
| --- | --- | --- |
| Procurement | 1-2 months | 6/2024 |
| Design of devices for each generator | 1-6 months | 12/2024 |
| Device Manufacture and installation | 6 months | 6/2025 |

- Demonstration of Funding Need

Pechanga has tracked and explored the availability of all other federal and state grant programs, tax incentives and other funding sources and can demonstrate this by the number of applications we have presented to funding agencies over the years and in the past months. Most of the new programs under the Inflation Reduction Act (IRA) and Bipartisan Infrastructure Law (BIL) are in the first phase of activities. These sources are not sufficient for the measures proposed here.  The Cogen Plant and Boost Box upgrades to our diesel generation are fossil fuel related upgrades, and most available grant programs are for renewable energy applications. We know of no grant programs available to Pechanga covering these two measures. Without an EPA CPRG program grant, the Cogeneration Plant costs would likely become an out-of-pocket cost to Pechanga. While we have avenues for government bonds, loans (including a U.S. Department of Energy loan) and bank financing, grant funding is preferred and would free up significant funding for additional tribal environmental projects and for other important tribal priorities.

Programs for Cogen Plant and Boost Box:

While the Inflation Reduction Act provides a 30% federal tax credit by expanding the Investment Tax Credit for “combined heat and power with overall efficiency” one of the requirements is that the project must begin construction before January 1, 2025, unless the project is a zero-carbon energy project, which extends the deadline to 2032. For projects greater than 1MW, projects must pay prevailing wages and maintain an apprenticeship program during construction and repairs/alterations made in the first five years of operation.  This includes a “direct pay” option for non-taxable entities. Pechanga is unsure if our implementation of the Cogen Plant can meet the “begin construction” deadline of January 1, 2025. While we will attempt to fast track this project to obtain the tax credit, this project still requires engineering, approvals, procurement, ordering of equipment, and construction. Initial designs for the Cogen Plant do not envision a zero-emissions option, and we are not aware of available commercial zero-emissions Cogen applications which do not require land base which is unavailable at our small reservation. We have mitigated our past cogeneration system with solar and will attempt to future mitigate carbon emissions from the Cogen Plant through the battery application and through other available technologies as they are presented to us.

Funding Programs for Battery Backup:

We include battery back-up in this grant application, as it is an integral part of the Cogen Plant project. There are other grant programs that are applicable to a battery backup system. Most programs are competitive, requiring significant resources to pursue and plan for seeking funds. Other grant programs are smaller so provide only a portion of funding. The grant programs we have and are considering include:

California: Self-Generation Incentive Program (SGIP) and the Long Duration Energy Storage Program. Pechanga has not yet applied for either program as they are not yet open for this project timeline.  Further, SGIP may not be applicable to this battery system as our power plant may not be a customer or a California utility subject to this state program.

Federal: U.S. Department of Energy Clean Energy Deployment on Tribal Lands (Pechanga plans to apply for this in May, 2024); U.S. Federal Emergency Management Administration BRIC program (Pechanga’s Hazard Mitigation Emergency Plan related to this round of funding was not specific as to energy funding so does not qualify); the U.S. Department of Energy Grid Resilience Tribal Formula Grants provides limited funds which could be used for PWE, but which are allocated to an urgent utility pole-replacement project. The Tribe also applied for the BIA’s Tribal Electrification Program grant for a battery storage project but was not awarded the grant under the first round of funding. BIA has encouraged the Tribe to apply again when the second round of funding becomes available.

Additionally, the Inflation Reduction Act provides a 30% federal tax credit by expanding the credit to energy storage projects. We will seek to apply these funds to the battery storage project.

- Transformative Impact

Both combined heat and power cogeneration and battery storage are proven technologies that are commercially available and have predictable outcomes. However, very few applications of these technologies, used together, is reported in Indian Country. Indian Country does have significant opportunity for cogeneration at casinos, for commercial sites, for housing and for other uses. Pechanga seeks to be a leader in Indian energy and our successful use of these systems will convince other tribes to generate power on-site for large commercial or industrial enterprises, and to store excess energy using batteries for self-sufficiency and to enhance tribal sovereignty. The combined use of our Cogen Plant and Battery back-up will demonstrate climate emission reduction. Pechanga has been active in giving tours of our existing utility to other tribes and to sharing information to assure successful projects are used by other tribes.

The Boost Box application is a pioneering technology using hydrogen to improve the combustion of diesel fuels and to clean the equipment for more efficient use overall. At a recent U.S. Department of Energy Tribal Clean Energy Conference, Pechanga reported its interest in this technology, inciting interest from many other Indian tribes seeking hydrogen applications for projects, especially in Alaska where significant diesel generation is used. While the Boost Box technology has been proven, hydrogen applications are not widely used at this time and not at all in Indian Country.  This technology is replicable, scalable and useful in the diesel generation sector, which is common in Indian Country, as well as for utility back-up in the general population. We can easily track the emissions improvement resulting from the measure. This measure, when proven by and Indian Tribe for improving diesel operations will be transformative for other tribes.

Section 2: Impact of GHG Reduction Measures

- Impacts GHG Reduction Measures Generally

Cogeneration systems require less fuel to produce a given energy output, and avoid transmission and distribution losses that occur when electricity travels over power lines. By capturing and using heat energy that would otherwise be wasted, Cogeneration systems operate far more efficiently than grid electricity and on-site heating. Typical CHP total system efficiencies are 60 to 70 percent. Depending on the application, this efficiency advantage can result in significant carbon dioxide emissions reductions.

Our 2018 data shows the carbon emissions from 9 Diesel generators is 8.36 tons/year. A decrease of 35% indicates a decrease of 2.926 tons/year. This number relates to the run-time of the diesel engines.  We find it important to reduce all emissions, including from the sources which do not run at all times.  Any deployment of fewer systems than our generators will be targeted to those diesel energy that have the longest run-times.

- Magnitude and durability of GHG Reductions from 2025 through 2030

| Measure | Estimated metric tons of CO2-equivalent emission reductions resulting from the measure 2025-2030 |
| --- | --- |
| Cogen Plant | 120,000 |
| 2MW/4MWH BESS | 5000 |
| Boost Box | 15 |

- Magnitude of GHG Reductions from 2025 through 2050

| Measure | Estimated metric tons of CO2-equivalent emission reductions resulting from the measure 2025-2050 |
| --- | --- |
| Cogen Plant | 600,000 |
| 2MW/4MWH BESS | 25,000 |
| Boost Box | 73 |

- Cost Effectiveness of GHG Reductions

| Measure | Cost effectiveness of GHG reductions (Requested CPRG funding) / (Sum of Quantified GHG reductions from CPRG funding from 2025-2030)] |
| --- | --- |
| Cogen Plant | $44,945,000/120,000=$375 |
| 2MW/4MWH BESS | $5,000,000/5000=$1000 |
| Boost Box | $900,000/15=$60,000 |

- Documentation of GHG Reduction Assumptions

The Technical Appendix is provided here in the form of endnotes to this Narrative.

The proposed new cogeneration system is expected to generate over 60,000 MWh of electrical energy. The standard California marginal emissions rate is 0.0004 tonnes (metric tons) of CO2 per kWh. Comparing the standard efficiency of a typical utility gas power plant in California (30%) and the expected combined efficiency of our cogeneration system (65%), the proposed cogeneration system will save over 24,000 metric tons of CO2 annually.

According to the Energy Storage Association, every MWH of battery storage can reduce CO2 emissions by an average of 300-600 metric tons per year.  Given the proposal for 2 1MW/4MWH BESS, We estimate an annual savings in purchases of energy due to the added BESS in the amount of 4MWh leading to an annual reduction in emissions in the amount of 2,000 metric tons of CO2 annually.

Implementing utility-scale battery storage through 2030 can reduce CO 2 emissions from California’s electricity sector by 8 percent (15.5 million tonnes CO 2 e on a life cycle basis) compared to exclusively using natural gas power to back up solar. Therefore, utility-scale battery storage has the potential to reduce the climate change and air pollution impact of California’s electricity sector, while increasing solar electricity grid penetration through improved grid flexibility.

Section 3: Environmental Results – Outputs, Outcomes, and Performance Measures

- Expected Outputs and Outcomes

Linkage to EPA Strategic Plan

The measures proposed here support EPA’s Fiscal Year (FY) 2022-2026 Strategic Plan. They will support Goal 1, “Tackle the Climate Crisis”; Objective 1.1, “Reduce Emissions that Cause Climate Change.” Under this objective, EPA will “aggressively reduce the emissions of greenhouse gases from all sectors while increasing energy and resource efficiency and the use of renewable energy.”

Outputs

Outputs from the implementation of these measures include:

- Installation of 7 Boost Box devices on 14 MW (7 of) diesel generators which will inject hydrogen into the diesel generators to improve the efficiency of diesel generation and reduce generator maintenance.

- Installation of 5MW of cogeneration natural gas turbines and supporting equipment including 4MW of cogeneration natural gas Caterpillar generators and 2MW of Battery storage.

- Progress Reports and a Final Report as specified in the grant documents.

Outcomes

The following outcomes will be realized from implementation of these measures.

- Reduction in cumulative metric tons of GHG emissions from 2025-2030: 125,000

- Reduction in cumulative metric tons of GHG emissions from 2025-2050: 625,000

- Reduction in annual amount of CAP and/or HAP emissions in low-income and disadvantaged communities in 2030.

- Tribal Energy Self-Sufficiency and Energy Sovereignty: Adding the measures proposed here will allow Pechanga to meet all its own electrical needs, except during peak times. It will also allow the Cogen Plant to provide all needed cooling and heating for the resort, including for the pool complex. It has been a long-term goal of the Tribe to be self-reliant and to exercise Tribal Sovereignty by using tribal rights and responsibilities to govern its own lands by providing its own services. PWE is investigating purchasing wholesale natural gas from another Indian Tribe that produces natural gas to operate its cogeneration plant.

- Reduce or virtually eliminate purchases of dirtier electricity from the CAISO grid: To meet today’s power need of up to 18MW, PWE must own generators or contract to purchase power in the amount up to of 18MW estimated for the month, then the day, then the hour; based on weather, historical usage data and other major factors that could influence power needs. With internals resources of approximately 5.9MW (not counting emergency diesel generators) and resources under contract from U.S. Department of Energy, Western Area Power Administration (WAPA) and tribal partners for hydropower from the federal dams of approximately 5.6MW, we can now generally meet 11.5MW of our need without making additional market purchases. Adding these measures will essentially eliminate our need to purchase other power.

- Reduce energy bills for customers in this disadvantaged community:  Power purchases (and the related transmission costs) are a large part of the PWE power rates. By reducing these costs, we lower all utility costs for tribal and commercial loads served by PWE. Lowering costs to the resort permits Pechanga to invest in other systems and charitable contributions that align with the Tribe’s culture and goals.

- Add high-paying, high quality jobs in the energy sector on the Reservation for tribal members and veterans: Many of our power plant jobs are currently filled by Navy veterans who have experience running power plants on ships and submarines.

- Increased resilience of power supply: PWE has the ability to island our electric utility operations and serve as a microgrid in the event the Southern California Edison (SCE) lines go down or in the event of a Public Safety Power Shutoff (PSPS) during high wind events.  These PSPS events impact the Reservation mostly during the summer months on the hottest days, causing dramatic impacts to the community. PWE can currently serve some of our loads in this event and must implement our load shedding policies if power demand is higher than our generation capabilities. These measures will permit for almost constant self-provision of electricity without use of the CAISO grid or the SCE electric system. Our tribal facilities served by PWE operate as community gathering centers that supply safety and other community services, so the ability to maintain electric power during emergencies is important to the whole Reservation and to the surrounding community.

- Increased resilience to climate change: Reducing emissions will result in increased resilience to climate change.

- Raised awareness of GHG Emissions among tribal members and Raised awareness of successful measures within Indian Country.  The measures will raise awareness of actions that will achieve this goal. Pechanga routinely describes its utility operations to other tribes and offers tours and other assistance. Successful measures will be shared with other Indian Tribes.

- Performance Measures and Plan

Performance measures to be discussed and documented in EPA reporting include:

- CO2 reductions

- Reliability and electrical outages

- Electricity costs by KWH.

Pechanga will monitor all GHG emissions through the term of its EPA CPRG planning grant.  Pechanga has always monitored its GHG and other emissions as required by EPA by its Tribal EPA office. Pechanga’s Environmental oversees GHG reporting for the Pechanga Band and provides recommendations for emissions control to enterprises owned and/or operated by the Pechanga Band. Ms. Wolfe, our environmental specialist is the Level 2 reviewer for the Pechanga PQAO and has experience in ambient air quality monitoring and assessments. Pechanga will compare its GHG emissions, especially CO2, before and after the measures.

PWE, as part of its utility operations, monitors its energy usage and purchases, outages, outages of SCE service, jobs and employment supporting the utility, and all costs which allow PWE to set cost-based rates. PWE reports to the Tribal Council and to General Membership at the General Council, as needed. The Tribal Council reviews all utility costs to approve utility rates.

- Authorities, Implementation Timeline, and Milestones

Authorities

The GHG Reduction measures will be approved through the Tribal and General Council before any final agreement is signed obligating the Tribe to any measure. To date, non-binding support for the measures has been overwhelming.

Responsible Parties

The parties responsible for implementing the measures include:

- PWE who will manage the grant and the interconnection of the Cogen Plant and Battery Back-up with SCE and CAISO and who will assist in the physical installation of all equipment and the metering and data collection from the facilities.

- Tribal Treasurer and the Pechanga Finance Department, who will manage funding sources, tax credits (if applicable) and any needed loans or bonds.

- PDC who will manage procurement of all goods and services, and who will house the Cogen Plant, Boost Boxes and other equipment, and who will operate and maintain the equipment.

- Subawardees will include:

  - Elen Consulting, Inc., the engineering firm who has worked with Pechanga for decades and who has designed the existing system and who has done the studies and preliminary designs necessary to conceptualize the Cogen Plant and related equipment.

Implementation Timeline/Milestones

| Activity Number | Activity | Length of Time | Quarters |
| --- | --- | --- | --- |
| 1 | Grant Agreements | 1 Month | Q1 Year 1 |
| 2 | Hiring/Procurement | 3 Months | Q1-2 Year 1 |
| 3 | BESS Design | 3-6 months | Q2-3 Year 1 |
| 4 | BESS Construction | 6 months | Q3-4 Year 1 |
| 5 | BESS Start-up and Commissioning | 1 month | Q4 Year 1 |
| 6 | Design of BoostBox HODT devices for each generator | 1-6 months | Q2-3 Year 1 |
| 7 | BoostBox HODT Manufacture and installation | 6 months | Q4-5 Year 2 |
| 8 | Cogen Plant Design | 8-9 months | Q2-4 Year 1 |
| 9 | Cogen Plant Procurement | 2-3 months | Q5-6 Year 2 |
| 10 | Cogen Plant Construction | 24 months | Q7-14 Years 2-4 |
| 11 | Cogen Plant Commissioning | 4 months | Q15-16 Year 4 |
| 12 | Cogen Plant Training | 4 months | Q17 Year 5 |
| 13 | Data collection, quality assurance and Semi-annual and Final Reporting | Throughout grant period | Year 5 |

| Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Section 4: Low-Income and Disadvantaged Communities

- Community Benefits

Pechanga’s homeland is considered disadvantaged due to its status as an Indian Reservation. On the Climate and Economic Justice Screening Tool, Tracts number 06065043257 and 06065043254, the Pechanga Indian Reservation is indicated as “disadvantaged”. The EPA EJScreen Tool also indicates higher than average (compared to the US) ozone, high traffic proximity, hazardous waste proximity, and wastewater discharge. It is also in the 90-95 percentile for wildfire risk.

The direct benefits of the measures on the population living on the reservation includes cleaner air and reduced risks to the impacts of climate change, including reduced risk of wildfires and extreme weather events. Indirect benefits to all tribal members, and to the tribe itself include energy self-sufficiency, energy sovereignty, lower energy costs, and improved electric reliability.  Other indirect benefits include new high-paying power plant jobs and related workforce training as described below.

Pechanga plans to utilize its existing Cogen Plant staff and Tribal EPA office to monitor, assess, quantify and report to their Tribal Council and to the EPA indicators from the measures, including the energy production, energy savings, energy wholesale purchases from CAISO, air and water emissions from the Cogen Plant and Diesel generators in order to track the benefits of the measures and to track any other benefits and disbenefits of the measures. Additional air quality measurement tools will be developed, tracked and reported as part of Pechanga’s CCAP.

- Community Engagement

The Pechanga Band of Indians is a true democracy, which provides a level of community engagement that is likely unrivaled by other applicants. The Tribe requires clear community engagement and official voted approvals.  All tribal decisions are made by the General Council which includes all voting members of the Tribe. The General Council has discussed grant application procedures and has delegated certain application permissions to the Tribal Council, who is the tribe’s elected body. This application submission has been approved through that process.

The General Council must vote in favor of the measures. The process for General Council approval requires a staff presentation to and approval by the Tribal Council, then advance notice and a presentation of the issues and vote at a General Council meeting (which are held monthly and as otherwise needed).  The Cogen Plant and Battery Backup has been presented informally to the Tribal Council without objection and will begin the formal approval process in Spring of 2024. The Boost Box measure is within the delegation approval provided by the General Council to the Tribal Council, however, all measures will likely be presented to the General Council as part of the grant application report.  Generally, the General Council has supported environmental mitigations, energy efficiency, energy sovereignty and improved technologies.  We anticipate approval of all measures by vote of the General Council.  The presentations described here are being fast-tracked due to the need to “begin construction” in 2024 to obtain tax credits. We anticipate approval in June of 2024.

Section 5: Job Quality

Before 2002, the area which is now the Pechanga resort was a rural area.  It is now one of the largest resorts in the United States with 1,100 AAA 4 diamond hotel rooms, gas station, golf course, a casino, spa, pools, RV park, concert venue and many other amenities. The resort employs more than 4000 people, with wages starting for non-technical positions at $18/hour. It is the second largest private employer in Riverside County.

There is a clear commitment to paying exceptional and market-based wages for all workers, despite prevailing wage not being required by law. Pechanga also supports numerous charitable, job and training programs in the community at large. Employees receive family sustaining benefits and retirement contributions. Pechanga will incorporate labor and job quality standards into procurement activities associated with our measurers. Health and safety plans are developed in conjunction with the workers, including anti-harassment training for workers and management, OSHA training to minimize workforce hazards and supplemental health and safety training as needed. There are goals to hire Native Americans.

PDC Facility Operators Training Program:

Pechanga Power Plant Operators go through rigorous training program to ensure their knowledge of the equipment and controls, and their ability to maintain equipment and effectively resolve critical situations. Special attention is paid to training for operations during utility power outages and equipment malfunctions. Several years ago, Pechanga Facility Department designed and install a sophisticated Control System Simulator that replicate the actual Pechanga Power Management and Control System (PMS) and is used for the initial and follow-up periodical training of System Operators. Many possible emergency situations are programmed in the PMS Simulator and the Operators are trained to quickly and efficiency resolve these issues followings written procedures. Operators are periodically tested on PMS Simulator on their knowledge of the control systems and Operation Procedures.

Pechanga Operators Equipment Maintenance Training program includes the initial and follow-up periodical training on maintenance of the specific equipment and systems. Operators are trained to maintain the specific equipment using Operation and Maintenance and Support Information Manuals (OMSI) that are available in Pechanga Technical Library for each different type of equipment and system. Operators attend technical seminars and classes provided by equipment manufacturers including Solar Turbines, Caterpillar Generators, G&W and S&C 12kV switchgear, etc.  Each Operator are required to complete minimum of 40 hours of initial training and 20 hours of the annual follow-up training.

Pechanga has succeeded in developing high-quality, family-sustaining jobs. Employment at the Pechanga power plant.  There are currently 14 full time power plant operators.  Adding the measures proposed here will require 12 additional power plant operators.

PWE Utility Coordinator:

PWE intends to hire a Utility Coordinator with an engineering degree. This position who will work closely at the South Central Power Plant with the PDC operations staff and will assist in the construction activities, interconnection work, supervision of contractors and on site inspections of construction activities.  After construction, this position will essentially manage onsite generation activities from the utility perspective such as by assisting in power planning, fuel agreements, coordinating power output with other energy purchases and similar utility related functions.  We propose that this grant will cover half of the cost of this FTE.  We estimate this professional engineering position will provide a very high quality job for a tribal member or other community member.

Section 6: Programmatic Capability and Past Performance

  - Past Performance

Pechanga has a history of excellent performance on federal grants. There are currently approximately Add # grants being performed at Pechanga. During the formation of PWE and since the utility’s formation, PWE has performed and administered 2 major State of California grants, and at least 6 federal grants and technical assistance awards (mostly U.S. Department of Energy and U.S. Department of Interior) for utility projects and studies.  The following are five examples:

  - Reporting Requirements

For all listed grants, we have an excellent history of meeting reporting requirements under the agreements. Interim and final reports were acceptable to granting agencies. We adequately and timely reported on progress toward achieving the expected outputs and outcomes under our agreements. In some cases, extensions of time were granted to allow for pivots in direction to accommodate initial grant findings or to allow for further data gathering.

  - Staff Expertise

To understand Pechanga staff, one must understand our government structure.  All measures will be performed and administered by the Tribe through its official channels and authorities. There is a top-down leadership, with excellence expected at each level. Pechanga is led by its General Council, made up of all members of the tribe. The General Council elects the Tribal Council. The Pechanga Tribal Council consists of six members and one chairperson. General elections are held every two years. If a vacancy occurs, a special election is held to fill the vacant council position. The tribal council meets at least on a monthly basis, and reports to the General Membership (which meets at least once a month). The tribal council sets policies, administers government programs and executes the will of the General Membership. The General Membership, by law, must vote on all Pechanga Reservation land-use decisions. The tribal chairperson and members of the council are charged to uphold and enforce the Pechanga Band's Constitution, bylaws and tribal ordinances. They are also responsible for upholding the rights of each tribal member, without malice or prejudice. The tribal council members are obligated to act always in the best interest of the Pechanga Band.

Mark Macarro is the duly elected Tribal Chairman of the Pechanga Band of Luiseño Indians in southern California. Chairman Macarro was first elected to the Pechanga Tribal Council in 1992 and is currently serving in his 27th consecutive year as Tribal Chairman. Throughout his tenure, Macarro's vision for Pechanga has been to see the Band strengthen its political self-determination and economic self-sufficiency while maintaining its distinct and unique cultural identity. He holds a B.A. in Political Science from the University of California, Santa Barbara. Mark is married to Holly Cook Macarro (Red Lake Band of Ojibwe) and is the proud father of four children.

Amy Minnear (Pechanga tribal member) is the Tribal Treasurer. Mrs. Minnear is responsible for all funding matters at the Tribe. See Resume. Mrs. Minnear works closely with the Pechanga Finance Department. The finance officer for this grant will be Ivan Gonzales, Accounting Manager, See resume.

PWE is an arm of the Pechanga Government, responsible to the Tribal Council, as the utility regulator. Pechanga Western Electric provides electric utility services to customers on the Pechanga Indian Reservation. Customers include the Pechanga Resort and Casino, the Pechanga Government Center, Recreation Center, residential customers, Health Center, and private commercial loads. PWE’s General Manager is Pi-Ta Pitt (Warm Springs tribal member). See Resume.  Mr. Pitt is a graduate of Columbia University and has served the Bonneville Power Administration. Mr. Pitt has successfully stewarded the growth and success of PWE.  He coordinates PWE operations with other arms of the Tribal Government, customers, utility partners and city, state and federal partners.

PWE will work closely on this project with the Pechanga Development Corporation (PDC), operator of the Pechanga Resort.  The GHG emission reduction measures will be located at the Pechanga Resort power plant. The PDC is led by a five-member board of directors that is elected to two-year terms by Pechanga Citizens. The existing power plant will be expanded to accommodate the Cogen Plant and other measures. PDC leadership includes Gary Senz, Facilities Director for PDC. Mr. Senz will assist in the development and construction of the measures and in the operation and maintenance of the measures after installed.

Pechanga’s Environmental Protection Office will be actively involved in all aspects of emissions control. Pechanga’s Environmental oversees GHG reporting for the Pechanga Band and provides recommendations for emissions control to enterprises owned and/or operated by the Pechanga Band. Pechanga’s Environmental Department includes Edmundo Hernandez (Interim Director of Environmental) and Tiffany Wolfe (Environmental Specialist). Mr. Hernandez holds a Bachelor of Science in Environmental Science and has over nine years of experience as an environmental professional. Mr. Hernandez has experience as an ambient air monitoring station operator and oversees the Pechanga Primary Quality Assurance Organization (PQAO). Ms. Wolfe has over 15 years of experience as an environmental professional. Ms. Wolfe is the Level 2 reviewer for the Pechanga PQAO and has experience in ambient air quality monitoring and assessments.

Pechanga intends a subaward to Elen Consulting, Inc. for the design, engineering and oversight of the technical aspects of the Cogen Plant. Pechanga has contracted with Elen Consulting, Inc. since the initial installation of infrastructure at Pechanga and is a dedicated member of the Pechanga utility team. Elen Consulting, Inc. is an award-winning mechanical, electrical, plumbing and lighting design firm known for its exacting engineering precision and service oriented client care. Pechanga’s lead utility engineer, who has successfully designed the tribal electrical infrastructure is Dmitriy Nathanson, P.E. (Electrical), P.E. (Mechanical), RCDD (See firm resume and Letter of Support. With over 30 years of experience in the fields of mechanical and electrical engineering Mr. Nathanson has extensive knowledge of the most effective and advanced HVAC, power, lighting and communication systems for a broad range of applications.  He has developed a special expertise in design-build and value engineering services for civil, commercial, urban, residential, industrial and infrastructure and military projects. As one of the founding principals of Elen, Dmitriy is well known for his ability to find innovative engineering solutions which have met and exceeded Pechanga’s needs and expectations.

Native Energy Resources Counsel, LLC, the law firm who has worked with Pechanga during the origination of PWE will provide legal and related energy services for acquisition of services and equipment, the interconnection of the facilities, and other power or transmission related legal efforts. Partners include Margaret Schaff (See Resume) and Evan DeWitt (See Resume).

Section 7: Budget

- Narrative

See attached Narrative.

- Budget Detail

See attached budget spreadsheet.

- Expenditure of Awarded Funds

The finance department manages the financial administration of all the Tribe’s grants. Grants are proposed by departments based on need along with consideration by the legal, purchasing, finance and any other relevant department. Then the department requests authorization for the Tribal Council to apply for the award. Once approved, grant applications are reviewed and submitted to agencies for consideration. If the grant is awarded by the agency, the department acts as the programmatic contact for the award while the finance department acts as the financial point of contact.

The Tribe requests funds on a quarterly reimbursement basis. Expenditures are tracked using fund accounting. Awards are assigned a number and that number is used for all transactions. Reporting is done in accordance with the terms of the award by both the programmatic and financial point of contact. Departments receive monthly and quarterly revenue and expenditure reports for grants to monitor accuracy and allowability of expenditures.

The Tribe segregates the programmatic and financial functions of grant management. Transactions are reviewed throughout the AP transaction cycle for, budgetary compliance, allowability, timing and approval. Vendor management is performed by the purchasing department. Vendors are reviewed for compliance with 2 CFR 200. Supporting documentation is retained by the tribe on site for three years then transferred to our offsite storage.

- Reasonableness of Costs

The estimated cost of the cogeneration plant is based on current equipment costs and does not include cost escalation. We obtained costs for all major equipment including Cogeneration Turbines, Gas Generators, Heat Recovery Steam Generators (HRSG), Absorption Chillers, Cooling Towers, Battery Energy Storage System (BESS) from manufacturers and their local vendor. The building costs are estimated on $/sq.ft. bases using current bench-mark costs in local construction market. Costs of materials, minor equipment and labor are estimated based on published US Means Construction Costs.  These bottom-up type cost estimates vary compared to the historical data for recently locally constructed similar facilities for correctness and reasonableness. Including 10%-20% contingency is recommended to address possible escalation of construction costs and volatility of the construction market.

Technical Appendix

See: https://www.epa.gov/chp/chps-role-decarbonization#:~:text=CHP's%20key%20roles%20in%20a,on-site%20reliability%20and%20resiliency.

Id.  See also:

See https://www.caiso.com/TodaysOutlook/Pages/supply.aspx.

See Footnote 2.

https://www.epa.gov/energy/electricity-storage

vi.

https://markets.businessinsider.com/news/stocks/clean-hydrogen-leader-boostboxh2-announces-results-of-independent-testing-averaging-10-diesel-fuel-savings-per-gallon-and-70-reduction-in-emissions-1028172145?op=1

Inflation Reduction Act of 2022 (Public Law 117-169).  Section 48(E) (ITC) Section 6417 (Direct Pay)

https://www.cpuc.ca.gov/sgipinfo/

https://www.energy.ca.gov/programs-and-topics/programs/long-duration-energy-storage-program

https://www.energy.gov/articles/doe-announces-50-million-tribal-clean-energy-projects

https://www.fema.gov/grants/mitigation/building-resilient-infrastructure-communities

https://www.energy.gov/gdo/grid-resilience-statetribal-formula-grant-program

Inflation Reduction Act of 2022.  Section 48(E) (ITC) Section 6417 (Direct Pay)

US Energy Information Administration, State Electricity Profiles, US Profile, Table 7 (emissions)

US Energy Storage Association.  See also https://climate-transparency-platform.org/sites/default/files/knowledge_centre_files/Greenhouse%20Gas%20Emissions%20Accounting%20for%20Battery%20Energy%20Storage%20Systems%20_BESS.pdf

See: “A. Balakrishnan et al., "Environmental Impacts of Utility-Scale Battery Storage in California," 2019 IEEE 46th Photovoltaic Specialists Conference (PVSC), Chicago, IL, USA, 2019, pp. 2472-2474, doi: 10.1109/PVSC40753.2019.8980665. (https://ieeexplore.ieee.org/document/8980665)